Adversaries or Partners?

Developing Best Practice Guidelines for Partnering in Construction

Case Study Report:

Bovis & Marks and Spencer

CONFIDENTIAL

Bovis and Marks and Spencer

A case study in construction ‘partnering’

Executive Summary

Introduction

1.0 Relationship Background

1.1 The Organisations

1.2 The Long Term Relationship

1.3 Project Description

2.0 Project Story

2.1 Pre-Construction

2.1.1 Clarifying Project Objectives – preparing for the development

2.1.2 The Tendering Process

2.1.3 Tender Evaluation

2.1.4 Team Selection

2.2 Construction

2.2.1 Managing Client Expectations

2.2.2 Project Complexity

2.2.3 Team Building

2.2.4 Communications

2.2.5 Management of Construction Progress

2.2.6 Completion

2.3 Post-Construction

2.3.1 Review of Construction Process

2.3.2 Review of Operational Store

3.0 Case Study Review

3.1 Construction Process Review

3.1.1 Key Issues from the Project

3.1.2 Improvement Suggestions

3.2 Store (Product) Review

3.2.1 Key Issues for the Store - Meeting Objectives and          Maintaining Ambience

3.2.2 Improvement Suggestions

4.0 Summary and Conclusions

4.1 Summary

4.2 Conclusions

Appendices

- Interviews

- Newsletter

- Project Appraisal Questionnaire

Adversaries or Partners?

Case Study Report: Marks and Spencer, Bolton

Executive Summary

The key findings of the investigation into the Bovis / Marks and Spencer relationship, based primarily upon a detailed case-study of the M&S Bolton project, were as follows:-

### Project Specific Issues

- Long-term partnering allows added opportunities for organisational and project learning which can influence strategy and policy.

- Benefits from continuity for members of the construction team are transferred to the client

- Marks and Spencer state preferences with respect to Bovis personnel seeking experience and understanding

- One of the key aspects of M&S  / Bovis projects is the atmosphere of learning lessons and of continuous improvement which exists.  This fosters the sense of team-working and commitment to successful completion and to working together on future projects.

- All members of the construction team had worked together previously (as had many of the sub-contractors) this helped with the shared understanding of the quality that the client expected.

- Impressive track record of project participants from previous M&S projects

- It is important to develop an approach to dealing with problems in a conciliatory manner

- Consider the procurement route and the effect this may have upon relationships

- Consider the completeness of design when the project is tendered on a single stage tendered project

- The ultimate aim is to satisfy the clients objectives and at the same time maintain the store’s pleasant ambience

General Issues

- Essential to the success of partnering with repeat clients is the long - term relationship with key sub contractors that has been established over many contracts.  Repeat ordering means that their management, supervisors and operatives become fully familiar with client requirements and the management contractors own working practices.

- Responsiveness to the market and a flexible approach to working together help in the development of sustainable long - term relationships.

- Partnering is about developing long term relationships and adding value to the clients business by understanding their business and meeting their building needs more effectively.  By growing clients in this manner the contractors own business will develop and the perception of an industry beset by adversarialism will change as contractors, design teams and sub-contractors seek closer working relationships in a new working philosophy which partnering should embrace.

- Client focus and accurately identifying their needs is a measure of successful partnering.  Satisfied clients lead to repeat work.

- Flexibility in approach is essential in diverse and rapidly changing construction markets

- Develop long term relationships as this permits continuity of experience, of understanding and of client understanding.  Ultimately this permits a higher quality service to be provided to the client.

- select the right people with the relevant experience, understanding and / or an identified ability to learn what is required

- construction is a ‘team’ business and this way of working needs to be encouraged.  This should not be left to chance.

- construction is a complex activity involving many players with multiple physical interfaces on site and even after the right people have been selected a quality management system is required to ensure the construction process occurs efficiently, effectively and elegantly etc… (Bovis QMS)

- the review process is an essential part of learning and continuous improvement and this occurs throughout the project and ideally as a separate exercise after project completion to harness lessons most effectively

- partnering is about changing mindsets, working together for mutual benefit and embracing the future positively

##### Introduction

This report is based upon a case study of a single construction project selected from a series of projects that together form the long-term relationship that is in existance between Marks and Spencer and Bovis Construction.  The nature of construction means that a large number of organisations are involved in any one project.  The contribution of these organisations is acknowledged now as it would not be possible to document in detail every contribution and relationship throughout the project.  Essentially this report considers the relationship between a client and management contractor, although other organisations from the design team and subcontractors are mentioned when appropriate.

The case study is presented in three sections.  The first section sets the scene.  The participants in the case study are briefly described, complete with a brief history and development of the long-term relationship and the background to the particular project to give the reader some contextual understanding.  The ‘story’ of a specific project (M&S Bolton) is provided in the second section concentrating upon key activities at pre-construction, construction and post-construction phases that can be perceived as best practice in achieving a successful project outcome.  The final section identifies lessons for future practice and opportunities for continuous improvement identified from this case and from more general experience of participants.  A summary is provided drawing together some preliminary conclusions that will subsequently be verified and synthesised with data from other case studies.

Bovis and Marks and Spencer provide the industry with a mature example of organisations working together, 75 years in fact, to each others benefit in what in popular understanding can be considered the landmark example of ‘partnering’ in construction.  Nearly 2000 projects have been completed around the world, in the UK, continental Europe, the USA and the Far East.  The nature of this relationship has been subject to change over the years due to the presence and departure of particular key individuals and in response to market forces.  A flexible approach to what is required in the market at a particular time can be said to personify the nature of the relationship.  This flexibility and willingness to change must be considered as an important factor when trying to identify why the relationship has endured.

## Conducting the Case Study

It is difficult to capture the complexity of a long-term relationship based upon a single project but this report will seek to illustrate how previous knowledge, goodwill, trust and mutual respect help facilitate the satisfactory completion of difficult construction projects for all parties.  This report provides a combination of an historical analysis and an illustration of the maintenance, development and management of the relationship on a ‘project specific’ basis, in this instance M&S Bolton.  This is followed by an attempt to identify good practice in dealing with project ‘problems’ and to establish the importance of good relationships between team members.

Initial discussions with both the client and contractor Project Managers identified a number of key areas of concern for the project stakeholders that need to be considered throughout the construction process on any project.  The emphasis of the investigation was upon relationships and dealing with problems that arise.  The key issues which were identified were as follows and are developed in the case study:-

Design - in particular the completeness of design at tender stage and the issuing of variations, the relationship between design team and contractor, specific problems of ‘cut and carve’ projects

Quality - right first time mentality and defect free construction, attitudes to snagging

Programme - problems with ‘cut and carve’ and the extent of early liaison with store manager concerning programme

Cost - how does a lump sum, fixed price contract affect the relationship between parties?

Safety - responsibilities of construction team members

Communications / Store Issues - interactions between key people and processes in the production of new facility, interface problems between retail and construction, the need to keep the store operational and client happy

Focusing upon these issues allowed the different perspectives of stakeholders to be contrasted and to see how these are dealt with in practice.  Wherever possible triangulation of data from the three key sources, namely client, contractor and design team in relation to the key issues is undertaken to strengthen the case study findings.

1.0 Relationship Background

This first section in this report will provide a background to the organisations involved in the long-term relationship, some details of the history of the relationship and an outline of the specific project that was investigated to illustrate how a partnering approach to construction projects operates in practice.

1.1 The Organisations

Bovis

(copy from Northern Foods for general background)

Marks and Spencer plc are regularly identified as one of Britain’s most successful and efficiently managed companies in the business press.  The Marks & Spencer open secrets of success have seen a focus quality, value for money and emphasised the importance of human relations (Tse, 1985).  Also, from Marks and Spencer’s mission statement the values of the organisation can be identified:

‘Our aim is to create an international retailing business, meeting local needs but integrated in such a way as to allow expertise and experience to be shared throughout the Group.  We are building on the traditional strengths of Marks and Spencer: a reputation for high quality and good value, a first class procurement base, an excellent team of people and highly professional management.’  Annual report and financial statements (1990)

This clearly has implications for the construction industry.  Marks and Spencer are an important client due to the demands that they make; their store redevelopment programme; and, their annual capital expenditure on construction works.  Data collected for Building Magazine regularly sees Marks and Spencer in the Top 10 clients in terms of total value of work placed.  As a major retail organisation with an emphasis upon quality there is a need for their in-store environment and general ambience to reflect this.  This requires a particular feeling in their stores and this is replicated around the country.  Marks & Spencer are an important and extremely demanding and challenging client for the industry.  They are a client with high expectations and stringent contractual terms.  Marks and Spencer are at the forefront of client-led improvement initiatives and this helps to set new standards for the industry.  A demanding customer traditionally drives the process of innovation in retailing and manufacturing; this is increasingly becoming the case in construction.

1.2 The Long Term Relationship

Bovis and Marks & Spencer have been working together for over 75 years.  Over this period of time the specifics of contract types and project management has been subject to change but the nature of the relationship in essence has been collaborative and based upon a belief in a ‘partnering’ attitude and philosophy.  A high level of mutual trust and understanding between each organisation has developed in these 75 years which has created synergy and mutual benefits.  The development of the relationship is illustrated chronologically in table 1 identifying the development of the relationship in terms of the scope of Bovis’ responsibilities, the form of contract and nature of the relationship.  The table also identifies key changes:

| Chronology (Approx.) | Scope of Bovis Responsibilities | Form of Contract | Nature of Relationship | Identified Changes & Why? |
| --- | --- | --- | --- | --- |
| 60 years ago | Building Works | M&S/Bovis Agreement (Fee) | Partnership | Development of Fee system to raise standards of projects |
| 20 years ago | Building Works and Hard Finishes | Fee | Partnership | Continue improvements with repeat projects |
| 10 years ago | Building / Finishes / Equipment | Management and Design Manage Construct (DMC) | Partnership | Co-ordinated Fit-Out |
| 5 years ago | Design and Full Fit-Out | Two Stage D&B and Management | Partnership | Guaranteed Maximum Price for cost certainty |
| Current Situation | Turn Key | M&S Single Stage Lump Sum | Partnership | Full Risk and Fixed Price with client seeking certainty with respect to cost, time and quality |

Table 1:  Historical changes (from interviews with Les Chatfield and Colin Small)

# Historical Background

Bovis used to do the majority of Marks and Spencer construction work as management contractor with little risk to Bovis due to the management fee system and cost-reimbursable contracts.  During this period Bovis effectively became ‘the building arm of M&S’.  For a long time as part of the Bovis Construction organisational structure a separate Marks and Spencer Division existed.  This indicated the level of work that Bovis were undertaking for Marks and Spencer.  As Marks and Spencer were such an important client it is perhaps clear why there was such importance attached to continuity of personnel and the need to understand the ‘system’.  This could be done more easily if people could identify specifically with a particular division and particular types of projects.

In recent years Marks and Spencer have taken two key decisions that affected this ‘historical situation’.  About 10 years ago Marks and Spencer made the decision to widen the supplier base.  This meant sourcing additional but limited construction companies.  In order to do this Marks and Spencer use a professional and structured approach to managing sourcing and procurement.  This process involves assessing potential contractors on a number of criteria (competitiveness, suitability, experience, financial strength, quality standard, health and safety policy, workforce and employee management, workforce skills and qualifications).  This provides an element of competition and a benchmark for relative value for money.  With this also came the use of two stage and single stage ‘lump-sum’ fixed price contracts as opposed to ‘management fee’ contracts.  A further development here saw the lump sum tendering process that used to be carried out as a two-stage process (project tendered though not fully designed) become a single stage process (building tendered fully designed).

The business philosophy of quality, customer service, profit and growth remains the same although changes have been experienced over the duration of the relationship and how this is achieved is different.  The culture of business differs today yet the relationship remains and is highly valued by both sides.

## Current Situation

In reference to the current situation Marks & Spencer were referred to as being ‘bullish’ in their approach to construction procurement. Following a change of personnel in their Estates department it was noted that Marks and Spencer have adopted a more commercial approach to procuring construction works.  Marks and Spencer now operate with a number of pre-qualified contractors.  It may be that some form of job allocation is in existence but the fact remains that Bovis now work with Marks and Spencer in a competitive environment.  Now Bovis are treated like other major suppliers to the Marks and Spencer organisation.  Operating in an increasingly commercial environment these actions were heavily influenced by ‘the market’.

Marks & Spencer are an experienced and professional client and they are aware of the risks involved in construction.  They see partnering as an opportunity to focus upon core skills.  Marks and Spencer are a retail organisation and do not want or see it as necessary to develop skills in construction, other than being a professional client.  To be a professional client they must identify their requirements and communicate them effectively.  In order to develop an effective, well managed approach to individual building / project procurement Marks and Spencer have a multi-functional in-house team, who in conjunction with outsourced ‘preferred’ consultants, develop the project brief.  Marks and Spencer believe in disciplined in-house project management of the design, the construction brief and specification and of procurement.  Specifics of project procurement differ according to job in question and they are comfortable using a range of procurement routes depending upon what is deemed appropriate for each job.  Procurement options from practice include a commitment to (a) management contracting, (b) lump sum fixed price contracts (both single stage and two stage), and, (c) negotiated contracts.

Marks and Spencer still believe a firm and clear contract with all risks and responsibilities specified is required as part of the procurement process. This flexible approach to procurement is a benefit of developed relationships between organisations and is essential in a business environment that increasingly demands adaptability and tailored solutions.  The Bovis approach also changed and now it is unlikely that employees work solely on Marks and Spencer projects, rather they alternate between clients if possible to maintain ‘freshness’ and to enhance potential learning opportunities.  Marks and Spencer still value employees with experience and developing this is a vital part of employees learning and education programme.  Bovis are committed to becoming a global player and require global customers and hence Marks and Spencer remain an important client and ‘business’ centre.

1.3 Project Background

Marks and Spencer Bolton comprised a multi-storey extension and total refurbishment to an existing large town centre store.  Retail space in Bolton increased from 48000 to 68000 square feet by adding two new levels to the Deansgate store and following the closure of a ‘satellite’ store in the town.  As is usual on these types of developments, it was essential that the store remained operational throughout the construction process with minimum loss of trade and disruption.  The project entailed the addition of two extra floors and refurbishment of the existing floor space.  The contract value was approximately £9.1 million and the contract period was 12 months, October 1995 – October 1996.  The contract form used was the Marks and Spencer Design and Construct single stage lump sum.

This was a fairly complex project that had with access restrictions due to the stores town centre location.  Table 2, below illustrates details of the development from the stores perspective and identifies the final layout.  The layout at project start was the traditional multi-floor layout with Menswear and Homeware at the top level.

| Location within store | Pre-Development | Post-Development |
| --- | --- | --- |
| Ground Floor | 60% Food Hall 40% Textiles | Dedicated Food Hall Relocation of:- - ambient section from front to back of store - cold chain to main body of store installation of new produce shop, butchers shop, sandwich shop |
| Ist Floor | Ladies clothing Ladies accessories Lingerie | Ladies clothing |
| 2nd Floor | Staff Quarters Offices Warehouse | Menswear Ladies accessories |
| 3rd Floor | Roof level | Lingerie Childrenswear Homeware |
| 4th Floor | - | Staff Quarters Offices Warehouse |

Table 2:  Development details of Marks and Spencer Bolton

The project opened on time and has been trading successfully for over 12 months.  The development coincided with the ‘Manchester Bomb’ and the closure of the Manchester store had a positive impact upon trading in Bolton with customers travelling from the usual Manchester ‘catchment’ areas for their Marks and Spencer products.

2.0 Story of the Project

‘In construction there is a need to work together, to fulfil mutual objectives and to maximise profit.  This represents a complex balancing act for the construction team.’  (Tim Atkinson, Project Manager M&S Bolton, 21/3/96)

2.1 Pre-Construction Phase

### 2.1.1 Clarifying Project Objectives – preparing for the development

After initial feasibility studies had been undertaken on a number of conceptual schemes, dating back to 1993, the development at Bolton received board approval. This initiated a series of brainstorming and team building events ‘in-house’ amongst Marks and Spencer senior management (store manager, deputy manager, finance manager and personnel manager).  The aim of these events was to develop a strategy to cope with the imminent building works and to minimise their impact.  A ‘Supervision and Focus Group’ were formed and given the opportunity to put forward their comments and to pre-empt possible problems with the plans e.g. no sluice room was planned for the Food Hall, it was expected that staff would go to the 4th floor stockroom level.  As lift access is key to stock movement in Bolton this would have meant carrying water up staircases!  Also, with customer care in mind the Focus Group wanted to retain a public staircase (usually these are taken away with developments).  The Project Team accepted this idea and this illustrates how it is important to let the staff, as end users, challenge the development plans early enough so that their knowledge and understanding of the building can be utilised.

Having received the necessary approval from the Marks and Spencer Cost Evaluation Committee the design of the Bolton store was signed off very early as complete (Summer 1995).  As the project developed this created problems and the nature of the existing building became apparent and layout requirements changed as happens in the dynamic retail industry.  With existing stores pre-tender exploration presents a problem due to the disruption which this causes.  However expenditure on exploration at this stage can prevent expensive discoveries being found at a later date.  Historically in construction, ‘as built’ and ‘record’ drawings have not been as accurate as they could have been.  This is an area that could be improved and computer technology may provide a possible solution.

2.1.2 The Tendering Process

Following approval of the detailed design by the relevant board, Marks and Spencer Bolton was tendered in open competition with a total of 4 construction companies bidding.  The tender process was single stage lump sum and commenced in early July 1995.  The tender period was initially 8 weeks though this was extended due to additions to the package.  The M&S view was that this was a fully designed job although there were clearly elements where ‘risk’ was present due in part to the extent of pre-construction site exploration which is permitted in an operational store.

Bovis split the job into various work packages and at this early stage in a project it is usual for as much of the eventual team to be in place and working on the job.  If possible this team includes Project Manager, Construction Manager, Commercial Manager, Services Manager and a Design Manager.  The detail of who is actually involved depends upon the nature and requirements of the job.  Work packages would be split up and the design manager would assess the completeness of the design.  The eventual Project Architect inherited this design which had been signed of as complete by Marks and Spencer in the summer of 1995.  To produce a smooth running and successful project it helps to have a common link through the job from pre-tender to completion, ‘it pays to have a core team’ (TA) with the Commercial Manager identified as critical for financial management purposes.

As well as identifying the internal team, a Bovis delegation also went to visit the M&S store team to initiate the relationship between these parties and begin to understand the complexity and necessary logistics of the project.  This activity, building the relationship with the Marks and Spencer store team was something neglected by other tendering organisations.  The tender was submitted in late September 1995 and was evaluated by MDA (QS) and the Design Team.

### 2.1.3 Tender Evaluation

When evaluating a tender Marks & Spencer consider a number of factors such as:

- The people who form the contractor’s ‘team’

- The usual triumvirate of Cost, Programme and Quality

- Project complexity and the contractors understanding of this and their proposed Construction Method (especially on complex cut and carve job).  The contractors attitude to safety and care and concern for the public.  Their attitude towards snagging and defect free construction is also important

- Recent performance and how many Marks and Spencer Projects the contractor is currently working on

A post-tender evaluation meeting took the form of an interview between key people with a number of contracting organisations still involved.  For Bovis the Construction Executive (Colin Small), the Project Manager, Services Manager and Commercial Manager attended.  This is usual for this type of job.  Such a meeting would usually provide a brief introduction to the company, introduce to proposed team indicating previous experience, an outline of the proposed programme and construction method by the Project Manager followed by an illustration of maintenance and installation of store services by the Services Manager.  This is usually followed by a question and Answer session relating to ‘key areas’ of concern.

The decision as to who has won the job is usually provided within a few days. Bovis were not the cheapest on the list but won the job due to perceived ‘added value’.  Bovis were awarded the job in September 1995.  The approved design was novated to Bovis Construction with all the responsibility on the contractor to produce the design provided.  The design team maintain a duty of care to the client in respect of the design but at this point there is a significant change in the contractual relations between client and design team and design team and contractor.

2.1.4 Team Selection

The aim for M&S Bolton, indeed all M&S jobs is a ‘defects free’ job.  A worthy aim as this provides a better outcome for all parties (Construction Team including Management Contractor and Sub-contractors, Design Team, Marks and Spencer and their customers) as there is no need to go back and carry out repeat work.  The reality is that this is a difficult goal to achieve.  Bovis are managing a process and their job is to manage, control and motivate a large number of different people and organisations.  Who they choose to be part of this team represents some very important decisions to be made.  Teamwork and co-operation is required at a number of levels within any relationship; strategic level, management level, operational and site level.  When putting together any construction team there is usually a high level of opportunities for selection at the management and operational levels.  People and organisations are selected who appear comfortable with each other and would be able to work together.

Sub-contractors with proven records of working successfully in the past for Bovis or Marks and Spencer were selected.  Specific sub-contractor selection criteria which included levels of skill and expertise; ‘tried and tested’, based upon past performance in terms of cost, quality, safety and meeting programme requirements.  Bovis maintain an electronic database containing information regarding subcontractors’ performance on previous Bovis projects.  This resource is supported by personal knowledge of subcontractor organisations that naturally exists within the management staff.  Recommendations and references can also be passed on by word of mouth within the organisation if particular individuals have not worked with specific subcontractor organisations.  At Bolton there were approximately 35 work packages let.  About a quarter of these were considered as ‘key’ players by the Bovis Construction Manager.  These critical packages included general builder, mechanical and electrical, sprinkler installation, refrigeration, ceiling fixers, shop - fitting, steelwork and the roofing package.  In order to manage certain aspects of quality and reliability on some dimensions of the project, Marks and Spencer will in some instances nominate preferred sub contractors.

It was stated (AT) that a key requirement of a sub-contracting organisation is that they have a good site / project based manager.  It is good practice to interview this person prior to any engagement to acquire a ‘feel’ of their knowledge, understanding and personality.  Making the ‘correct’ choice here is important.  It is these people who Bovis will be working with and communicating with, an important question to ask is, Can you work with these people?

2.2 Construction Phase

2.2.1 Managing Client Expectations

Once the contractor is in place, Marks and Spencer consider the most important aspect of the project to be the ‘mission statement’.  They believe that it is here that the argument must take place in order to get a thorough understanding of the each others needs, and agreement on the process and demands of the project.  Effort at this earliest stage is important to avoid problems later in the project.  Further, M&S are what can be termed a ‘professional’ client due to the amount of work they undertake and expect high levels of health, safety and hygiene to fit their corporate image.  This provides a particular challenge for the contractor on Marks and Spencer projects in terms of the construction solution and method.  In operational stores their emphasis is upon safety, cleanliness, general appearance, signage and noise levels.

For Marks and Spencer, and any other retailer, the year is characterised by a series of key events which provide good sales opportunities; Christmas, January Sales, Valentine’s Day, Easter, Mothers Day, Fathers Day, the Back to School period.  In a 12 month contract it is inevitable that works and key dates will clash and this presents specific planning and programming objectives which it is necessary to work around.  It is likely to be in the contractors brief to avoid major disruption around these periods of time.  Both store and contractor must agree what this means in practical terms e.g. Bovis ‘avoided’ the Mothers Day peak by originally planning major activity the weekend before Mothers Day.  In practice this was changed to the Mothers day weekend itself i.e. sales had been maximised and the store carried less stock which needed to be moved.

# Also, during construction a key concern for Marks and Spencer is for the separation of construction activities from the rest of the store and for the safety of customers and staff.  Obviously the client wants the building to look like a store rather than a building site and the contractor must be aware of this and operate accordingly.  Also, in an operational store security is a key issue for the client and with 24 hour working this required the contractor to have a robust and rigorous system in place.

2.2.2 Project Complexity

Logistically Marks and Spencer Bolton provided a challenging and complex project for the following reasons:

- access very difficult

- number of work faces operational at any one time

- unforeseen programming and planning

This complexity again emphasises the importance of communication links with the store and the need to keep them informed about what is happening.  Sally Martin was the key link with weekly formal meetings with key members of the M&S store team, allied to frequent interactions on a daily basis relating to construction activities and progress.  Sally’s role at Bolton which was initially split between commercial management and dealing with Bovis, developed into a full-time liaison role between Bovis Management, the construction team, the store team and customers.  Her main concern to keep both staff and customers informed and happy in relation to the disruption and upheaval associated with a major construction project and to minimise the impact of the development on the commercial operation.  The issues of concern and potential problems the M&S store team face are obviously different to those of the construction team.  This illustrates the potential problem of differing perspectives on a construction project and the need for excellent communications.

### 2.2.3 Team Building

Team building is valued as a very necessary activity in developing relationships between the company and contractor.  This takes place in workshops, seminars and site visits.  Particular emphasis is given to developing the team of site manager, project manager and store manager.  For the construction team informal team building exercises such as ten-pin bowling and social evenings are an essential part of the construction process.

It is essential to foster a sense of ‘team’ togetherness amongst store staff as well as the ‘construction team’.  This helps to maintain the morale of staff during periods of construction that were stressful and frustrating.  At Bolton, the works seemed to continually impact upon the same people and it was necessary to take special attention of these staff.  Once Lingerie had moved to the satellite in February the burden repeatedly fell on the Ladies Wear and Food teams in the main store.  The continual process of de-merchandising and then re-merchandising created tensions and frustrations for particular staff members who were regularly affected by the development.  Of approximately 200 staff, half were seriously affected particularly wines and foods due to the need to move full racks of wine and the settlement of dust on the bottles.  Excellent communications are vital to deal with this situation and avoid abortive work.  Focusing and developing communication channels can help in producing an integrated and effective project team.

2.2.4 Communications

Successful construction relies upon effective and reliable communications.  Information exchange and keeping people informed were identified as key activities.  Project communications are at the end of a complex information channel involving numerous parties who needed to provide and receive information which was accurate and timely.  For example, Sally Martin’s liaison role with Bovis fed into a liaison with Marks and Spencer store staff.  The aim here was to communicate, to provide a physical presence, to be visual and to effect a trickle down of information from the focus team in a manner that was described as ‘fun but informative’.  There was also a need to follow up and review activities in a continuous evaluation process. This liaison enabled a ‘development update’ newsletter to be produced that aimed to inform staff of progress to date and future construction activities at the various work faces in the store.  The responsibility for Bovis is to manage store expectations so the client and his store team know what activities are taking place and where.  This is essential public relations that the contractor must be prepared to undertake.  Also, in conjunction with Ted Brown, from Advertising at Baker Street, Sally developed ‘tin-tin’ men that decorated the screening to provide more pleasant environment and also informed customers about the construction works that were underway.

The roles and responsibility Sally Martin was communicating to divisional team, providing a progress report and an assessment of the impact of the development on the sales performance of the store in relation to business sales performance, particularly during periods of major building activity.  During construction, weekly team meetings took place to manage the next phase of the development with the Management and Supervision levels, as well as monthly focus team meetings to update the general staff.  The weekly meetings were concerned with the immediate short term, the next phase, the bigger phase and floor by floor issues.  Focus team representatives were also given the chance to walk the backstage areas to see the work in progress.  ‘Seeing is believing’ and they are better equipped to communicate to their colleagues.  Also, an informal newsletter was also produced by Sally which aimed to make people aware of construction activities (see Appendix 2).

### 2.2.5 Management of Construction Progress

Once the project is underway Marks and Spencer feel that the onus is on the contractor and consultant to manage the sub contractors and suppliers and the risks involved.  To help with this Bovis operate weekly formal sub-contractors meetings for all packages once they are operational.  Other regular meetings to monitor and review progress include Design Team Meetings, Services Design Team Meetings, Policy Meetings, Foremans Meetings to monitor production, and Safety Meetings.  These meeting involve relevant people from the project whatever stage it is at and are relatively structured.  Unstructured Team Meetings are also held on a regular basis to develop team spirit.

Enabling works started in early December although the bulk of the job did not start in earnest until January (8th) after the Christmas and New Year peaks.  The tower crane went up in January and this was considered symbolic of the project starting.  Serious weather problems were experienced in January, February, and March that affected works.  The time of the year obviously needs to be considered when programming particular activities.  At Bolton, major work was being conducted on the roof in January and February.  This is not a good time to be working there for a town at the foot of the Pennines.  Throughout construction a number of ‘critical moments’ occurred.  The worst ‘pinch’ point to the store was when the screening to construct the scissor escalator was erected, two thirds of the way through the programme reducing original selling footage by nearly half and impacting upon visibility across the sales floor.  Another area that created some tension was with the breaking out of the old escalators and staircases, an activity that created lots of dust.  This pushed people to breaking point and a ‘janitor’ was provided by Bovis to deal with this problem.

This project required the planning of two programmes (referred to as 200% planning) in an occupied and operational building due to 24 hour working.  This created a situation were before each day shift there was a need to re-assess the previous nights activities and vice versa.  Unforeseen night-time or day-time activities could create problems and there was a need to continually re-assess and refine programmes.  In conjunction with this daily programming there was also a need to continually monitor and refine medium and long term programmes as construction progressed.  The programme was also very tight with little float where strategic operations such as refrigeration installation, lift installation and escalator installation are critical to maintain the smooth operation of the store.  The fact that virtually all weekends were worked emphasises this (originally only an approximate 40-60% were anticipated as being required).  The original programme slipped for a variety of reasons including the number of work faces, adverse weather conditions and communications from head office.  Considering these complications the construction team did extremely well to hand over only one week later than the original completion date.  As the project progressed there was a need to ‘re-phase’ the programme to ensure target dates were met.  Bovis were successful in providing Marks and Spencer with the benefits of additional and refurbished floor space on specific agreed dates as the project progressed.

# 2.2.6 Project Completion

To celebrate achievements the store team had a number of free social events during the building process for example, strawberries and cream during Wimbledon fortnight and free Breakfast and Bucks Fizz to mark new staff quarters hand over.  Other achievements such as when screens come down and the launch of the first central escalator operation were celebrated amongst the Marks and Spencer staff.  This was seen to be important in dealing with the disruption and developing the sense of progress and milestones being met.  The store was completed and became fully operational in the first week of November 1996.  As the construction works were completed on a phased basis this provided an opportunity for two opening ceremonies and two shots at publicity.  Celebrating achievements was a key aspect in rewarding and motivating staff, an example being the bucks fizz breakfast with top rated Michelin chef Paul Heathcote present at the opening of the food hall.  The mayor of Bolton also performed the cutting of the ribbon.  Nat Lofthouse opened the main store and opening events included a prize draw to win a car, a jazz band, pianist on a grand piano, face painting, makeovers and other activities.

2.3 Post Construction Phase

When the project is complete it is usual for project ‘post-mortems’ to take place.  These are useful in enabling people to reflect upon where things went well and where not so well and provide a formal learning opportunity.  They also provide an opportunity to formally close the project and maintain relations between parties in the calm aftermath of a construction project that can see tempers frayed and relations soured.  A review can take place at a number of levels in-house in construction and client organisations and inter-disciplinary.

2.3.1 Review of Construction Process

Marks and Spencer use a standard project appraisal questionnaire which is filled in by the construction team (see appendix 3) for post completion evaluation.  This post-contract review is undertaken following a structured agenda considering scope of works and to provide ratings for key parties (M&S / Consultants / Contractor / Sub-Contractors) and provides the client with a standardised form of data.  Large projects may also involve a formal review involving key players in addition to the project appraisal questionnaire.  For Marks and Spencer the number of variations issued and the number of snaggs provide a useful quantitative performance indicator for projects as they search for the snagg free job.

Bovis policy on Marks and Spencer projects is for the Project Manager to provide a summary report on the project relating to specific project performance prior to their in-house review.  This identifies areas to focus future improvement initiatives upon. Also, the degree of corporate thinking between Bovis and Marks & Spencer was embodied in a seminar held at Harrow fronted by Nick Penny, Marks & Spencer to review various projects completed in 1996.  This enabled a strategic overview of performance to be gained and consider other issues such as workload ‘peaks and troughs’ and programming and staff issues due to the potential overloads at Christmas and Easter for a major retail client.

2.3.2 Review of Finished Product

For the store, after construction work is complete there is still the task of making the extended and refurbished store work.  This presents another learning curve the store team need to negotiate i.e. how customers move around the building, which sales floor level are they paying on, do they go to the top and work their way down paying as they go?  These issues have an impact upon staffing levels and the service offered to the customer.  These are issues which must be faced on each store and obviously a great deal of knowledge and experience resides in store management who have experienced a major development.

3.0	Case Study Review

When reviewing a completed construction project it is useful to consider lessons and improvement suggestions in relation to the construction process and, the finished product.  Also, for a client like Marks and Spencer with a large development portfolio a number of ‘in - store’ issues are raised which offer an opportunity to improve future performance.  The construction industry and its clients must develop the ability for all parties to learn from their experience.  If lessons can be learnt this will help contractors and the Marks and Spencer Team (store and HQ).  This will ultimately benefit the customer in terms of less disruption during redevelopment and through shorter construction programmes.  Capturing knowledge from people who have experienced redevelopment is essential if the industry seriously wishes to improve the construction process.

3.1 Construction Process Review

3.1.1 Key Issues from the Project

From the case study a number of key issues can be identified that impact upon performance.

No. 1 - Approach to dealing with Problems

As identified in interviews with the Bovis and Marks and Spencer project managers at an early stage in the project, key issues of concern were design and subsequent variations, quality, programme, cost, safety and communication.  Different construction projects will have different critical elements depending upon job specifics but these will tend to be always related to the three key elements of cost, time or quality.  Looking back we find that the project was completed successfully although there were a number of minor problems relating to design issues and some financial disagreements.  At times friction existed between Design Team members due to inadequate initial surveys, building control issues and basic works co-ordination.  A key aspect of this job that created tension between parties was the project’s ‘complexity’ and the complex programming this involved due to specifics of the job and access problems.  This creates a need to manage complexity (due to building location and nature of the project) and the need to control cost in this situation.  Job specifics created a situation with lots of ‘work faces’ which presented co-ordination difficulties for M&S store team, sub-contractors and the main contractor.

The interviews indicated that these problems could have been worse if the relationship between the parties had not been one of ‘partnering’ and communications were very good.  Problems such as those mentioned above tend to be industry wide but can be compounded by fixed price contracts that offer limited scope for resolving problems.  Here, costs tend to be passed on and this can seriously affect programme.  The working relationship between the design team and Bovis, at a project focused level, were very good throughout the project.  A pro-active, conciliatory problem solving approach characterised the relationship between the design team and the contractor.  This was a two-way relationship.

#### No. 2 - Procurement Route

Whilst it is understandable for a client to seek certainty in projects, a feeling exists that the lump sum, single stage form of contract is not conducive to ‘partnering’ and the ‘non-adversarial’ approach implicit with a partnering approach.  If there are any changes the risk lies with either the contractor or the designer and this can lead to a combative situation.  The client has combined fixed price contracting with an increasing reticence to make changes on projects.  This has made life pretty difficult for the contractor.  Historically, project variations have presented contractors with an opportunity to improve income and it is understandable for clients to want to prevent this.

No. 3 - Completeness of Design

However, the above policy does raise a serious question of whether a building can ever be fully designed prior to the start of construction, particularly cut and carve projects.  At Bolton, the design was novated after it was signed off as complete and all the risk lay with Bovis.  Design completeness is a recognised problem with ‘cut and carve’ town centre jobs were compatibility and co-ordination between the design and the physical building is critical to project success when the initial design is assumed complete.  At Bolton, the completeness of design at the tender stage was questioned and the possible need for a design audit at the tender stage was identified.  Also, the extent of pre-construction surveys that were carried out was an issue for consideration.

3.1.2 Improvement Suggestions

Reflecting upon the project identified a number of areas that the team felt could be improved.  Risk and risk assessment is critical for complex projects such as Marks and Spencer Bolton and there is a need to identify areas of potential problems.  In the process there is a need to fully audit the design, the bill of quantities and to assess the tender market.  When all three of these have been completed the price can be fixed plus a contingency for unseen risks.  The more experienced the contractor the more accurately can this risk be assessed.  Improving the efficiency of the process will reduce costs.  With lump sum tendering it is important for the contractor to get involved a soon as possible to influence both design and buildability.  Also, for the construction team it was identified that maintaining the same team at submission, pre-construction and construction phases would have helped by providing a common link.  Bringing people on board as the project is developing can lead to ongoing ‘learning curve’ problems.

Also, the lack of accurate record documentation needs to be addressed.  If these do not exist on a project there is the need to conduct more extensive pre-development surveys that can help to reduce the risk profile on a project.  This needs to be balanced with the disruption which survey can cause in an operational store.  However this can be minimised if approached in a professional manner.  Improving record documentation and as built drawings is also necessary.

Other issues that were mentioned as areas which could be improved included the criticality of selecting the right sub-contractors, specification changes during construction, the importance of the post contract review and learning for future projects.

Job specific suggestions for improvement that may be relevant at other Marks and Spencer stores include:

- Totally removing asbestos ceiling tiles prior to starting main construction works

- Scaffolding the job in a traditional manner

- delivery and storage

- two stage tendering process would have helped to share the risk

All of the above had an impact upon cost but the learning curve provides opportunities for other projects.

3.2 In-Store Issues

Retail is a dynamic industry and on any project there are many unknowns (affect of Manchester bomb upon programme and opening dates, for example).  When stores are being re-developed teams must be prepared to change and flexibility is essential but this can be facilitated by effective communications.  Unfortunately, a problem the store experienced was the feeling of being part of a complex three way relationship between Baker Street and the Contractor, where communication problems between these parties could make life very difficult in the store.

‘The way particular events are dealt with, whilst not threatening the relationship produce friction and emphasises the difference in culture between client and contractor organisations and the need for effective communication to overcome this’.  (Sally Martin, 19/12/96)

Also, as this was a fixed price contract it was very difficult to effect changes. This had an impact upon the relationship as the project progressed and things were costing more than had been anticipated.  However through the focus and attitude of the team these problems were overcame.

3.2.1 Key Issues for the Store – Meeting Objectives and Maintaining the Ambience

As well as the need to meet the long term objective for any development it is important for the contractor to maintain a pleasant store.  During the redevelopment of an existing store what is important to the client is maintaining the quality environment and ambience which is provided for the customers.  The aim is to avoid extremes of heating and lighting and to maintain a high level of hygiene.  Specifically, areas of concern which tend to occur at the interfaces of construction and retail are:-

- hoardings screening construction work require to be clean and to a high standard.

- dust which is produced during construction can create a hygiene problem and merchandise must be protected.  At Bolton double layers of polythene were used as protection.

- lighting must be provided where screening affect the balance of natural and artificial lighting within the store.  At Bolton neon strip lights were utilised down the sides of the hoardings.

- security is essential on operational stores

Re-development invariably has a large impact upon a stores takings during construction works.  The role of the store team is to minimise this disruption and losses and ensure quality and a smooth operation is maintained.  The redevelopment of M&S Bolton resulted in estimated sales losses of £1.5 million.

Lessons learnt from store development include the importance of staff integration into the development process.  This was described as ‘inform staff- involve staff- celebrate with staff’ to ensure high levels of customer satisfaction are maintained.  Also, the timing of construction activities important to avoid key retail times.

3.2.1 Improvement Suggestions

A ‘Development Pack’ would be useful in providing details of contact points, equipment requirements and details of specific issues to be aware of.  The store does not receive the specification and has to challenge omissions.  Each store comes new to a development yet many areas must be consistent with previous developments.  These points can be very varied, but because there are few checklists one can think of the question too late to action.  Points Bolton challenged which were not covered by specifications ranged from:

- Sales floor fire bells located on the front face of columns.  These faces are key merchandise and display opportunities.  What was particularly frustrating was that 2 sales floors were fine and bells were on the column backs.

- No hand towel dispensers provided for sluice rooms.

- Electrical socket in ladies changing room located adjacent to only access door causing obstruction.

- Paper towel dispensers poorly positioned and could be hit by a door opening.

- No provision for sales floor customer seating.

When reviewing the early phases of the development plans, the ‘development’ pack could point the store to challenge the specification before it becomes a VORF (variation order form).  Benefits could arise from developing ‘learning nets’ of store liaison staff who have experienced development projects.  Also, embracing computer technology with such things as a virtual reality ‘walk through’ of the finished store would help with appreciating sight lines on each sales floor with respect to columns, tills and wardrobes.  This would help to sign off a lot of queries early on.

Merchandising Equipment is a key issue to all stores.  This is because Head Office layouts, display techniques and equipment mix required by the Buying Groups and Sales Promotion teams are decided on very close to the new buying season.  Stores are required to sign off, and are subsequently held to, requirements that are a year or more old.  The ‘16 week out’ redraw only allows minor amendments.  There has to be a better way of managing this situation, a pool of equipment funding was one suggestion.

4.0 Summary and Conclusions

From the project we can say that key issues to consider in partnering projects based upon this case study include:

- Develop an approach to dealing with problems in a conciliatory manner

- Consider the procurement route and the effect this may have upon relationships

- Consider the completeness of design when the project is tendered on a single stage tendered project

- The ultimate aim is to satisfy the clients objectives and at the same time maintain the store’s pleasant ambience

4.1 Summary

Experience from M&S Bolton has led to subsequent jobs following a two stage tender process including provisional sums in the lump sum and for elements of negotiation in the process.  Other procurement routes currently being pursued by Marks and Spencer include Management Contracting and negotiated two stage lump sum contracts.  Lessons from M&S Bolton are already filtering into Marks and Spencer procurement policy with other projects being procured by different routes as mentioned above.  The specific route depends upon a number of variables including Marks and Spencer requirements, the nature and complexity of the project and the capability of the chosen contractor.  Marks and Spencer now view Bovis as a supplier but it is worth considering how similar they are to other suppliers as the majority of the product that Bovis provide is not ‘built in a factory under controlled conditions in a repetitious manner’ (AT).  Also, Bovis provide a service, managing a process that is currently fragmented.  Opportunities for greater levels of standardization of both construction products and the process will be offered with new build and to a lessor extent with ‘cut and carve’ projects.

A trend in current Marks and Spencer operations and noted in other retail client organisations was their use of what could be termed ‘general’ managers as opposed to specifically ‘construction’ managers.  For example, the project manager at Bolton had a background in catering and the Marks and Spencer Food Group.  If adopted widely, this practice could help towards the transformation and development of the management process in construction.  However, the construction industry is facing a skill-shortage amongst operatives.  This can be related to the boom / bust nature of the industry and how it follows the economic cycle more directly than other industries and is most vulnerable to any recession and downturn in economic fortunes (Building, 19/9/97, p26-27, Cambridge Econometrics).  Also training is the first budget which is cut when firms are trying to cut costs and there is also a problem due to the lack of directly employed labour at work on construction sites.  An example of this on M&S Bolton was with the ceiling fixers who had suffered in this respect and where the lack of skilled craftsmen impacted upon the cost and programme of the project, albeit the issue had been resolved before completion.

4.2 Conclusions

Understanding the basis for ‘partnering’ success is clearly difficult.  Whilst it may be easy to attribute the success of the relationship to individuals, the development of shared understanding and developed personal networks is clearly one reason why the Marks & Spencer and Bovis ‘partnership’ has flourished for over 70 years and is considered a best practice example within the industry.

‘The relationship has changed and will change again in the future, but Bovis must be flexible and adaptive to meet this change positively and ensure that the client receives the service quality he expects…’ (Colin Small, 24/6/97)

Personnel may change but the core values and attitudes of a company which are shaped by these people evolve, take longer to become established and make it possible for organisations to work together successfully.  The nature of the relationship between Marks and Spencer and Bovis would seem to be based around long term thinking and mutual growth with an emphasis upon problem resolution and dispute avoidance.  Since the Latham Report (1994) references to partnering usually include the Bovis / Marks and Spencer relationship.  Whilst this relationship is different to many other examples of partnering it certainly illustrates the key benefits of customer focus; improved quality, cost effectiveness and speed; responsiveness; team spirit and innovation identified in ‘Trusting the Team’ (Bennett and Jayes, 1995).  This has been achieved in a retail environment that is becoming increasingly competitive, and as mentioned at the beginning of this report a critical factor is the flexibility inherent in the relationship which ensures the relationship endures despite external pressures for change.

Appendix 1

Interviews Conducted by the Research Team that helped in the production of this report in conjunction with various published material:

- Roger Aldridge, Estates and Store Development; Dr. Nick Penny, states and ConstructionServices, Marks and Spencer, 23/1/96

- Paul Johnson, Commercial Manager, Bovis 6/3/96

- Tim Atkinson, Project Manager, Bovis; Joe Sugrue, Project QS, Bovis 21/3/96

- Les Chatfield, Divisional MD, Bovis, 27/3/96

- Richard Hopkinson, Project Manager, Marks and Spencer, 1/5/96

- Tim Atkinson, Project Manager, Bovis, 2/5/96

- Andy Teague, Senior Construction Manager, Bovis, 2/5/96

- Phil Linsky, QS, Bovis, 2/5/96

- Andrew Dibley, Safety Manager, Bovis, 2/5/96

- Don MacLean, Project Architect, 24/10/96

- Mike Campbell, Hutter Jennings Titchmarsh, Structural Engineers, 24/10/96

- Tim Atkinson, Andy Teague, 18/12/96

- Sally Martin, Store Liaison, Marks and Spencer Bolton, 19/12/96

- Colin Small, Project Director, M&S Manchester, 24/6/97

Tse, K.K. (1985) Marks and Spencer: Anatomy of Britain’s most efficiently managed company Pergamon Press

Monthly Data compiled for Building Magazine by Glenigan Group.  See for example, Building, 19th September 1997 p 14.