Adversaries or Partners? IMI EPSRC Research Programme

University of Salford

Interview ‘Summary’ Report: M&S Bolton

Date: 		18th December 1996

Interviewee: 	Tim Atkinson, Project Manager, Bovis, M&S Bolton

Andy Teague, Construction Manager, Bovis, M&S Bolton

Location: 	BBC HQ, London

Interviewer: 	Stephen Allen

CONTENTS

1.0	Personal Background

2.0	Project Summary

3.0	Story of Project

Pre-Construction Phase

Construction Phase

Post Construction Phase

4.0	Project Review

Key Issues

5.0	General Comments

1.0	Personal Background

Both Tim and Andy have extensive track records with M&S having completed numerous successful jobs.  Tim Atkinson has worked on M&S projects for 17 years and recalled recalled 10 M&S jobs.  Glasgow, Sauchiehall Street; Worthing; Eastbourne; Warehouse ??; Stirling; Inverness; and Basildon consecutively in a dedicated ‘M&S Division’ with Chris Patton as MD.  These were followed by Marble Arch; Cardiff, Calderhouse Cross; and Bolton intermittently from the late 1980’s with Roger Maybe as MD which followed a change in market conditions and a move from working solely for M&S.

Andy Teague has worked on 12-15 projects in a similar timescale.

2.0	Project Summary

M&S Bolton comprised an extension and total refurbishment to a large town centre store which required to remain operational throughout the construction process with minimum loss of trade and disruption.  The project entailed the addition of two extra floors and refurbishment of existing floor space.  The contract value was approximately £9.1 million and the programme under 12 months.  The contract form was a M&S Design and Construct single stage lump sum.

3.0 Story of the Project

Pre-Construction

Pre-Tender: M&S Bolton was tendered in open competion with a total of 4 construction companies bidding.  The tender process was single stage lump sum and commenced in early July 1995.  The tender period was initially 8 weeks though this was extended due to additions to the package.  The M&S view was that this was a fully designed job although there were clearly elements where ‘risk’ was present due in part to the extent of pre-construction site exploration which is permitted in an operational store.

Bovis split the job into various work packages and at this stage in a project it is usual for as much of the eventual team to be in place and working on the job.  If possible this team includes Project Manager, Construction Manager, Commercial Manager, Services Manager and a Design Manager.  The detail of who is actually involved depends upon the nature and requireemnts of the job.  Work packages would be split up and the design manager would assess the completeness of the design.  The eventual Project Architect Don Mclean inherited this design.  It is important to have a common link through the job from pre-tender to completion, ‘it pays to have a core team’ (TA) with the Commercial Manager identified as critical for future accounting purposes.

A Bovis delegation also went to visit the M&S store team to initiate the relationship between these parties and begin to understand the complexity / logistics of the project.  This activity, building the relationship with the Marks and Spencer store team was something which other tendering organisations failed to do.

The tender was submitted in late September 1995 and was evaluated by MDA (QS) and the Design Team.  Bovis were not necessarily the cheapest on the list but it was stated that M&S are interested in a number of factors when assessing tenders:-

- Team

- Quality

- Cost

- Programme

- Understanding of the Project

- Construction Method (especially on complex cut and carve job)

- Attitude to Safety and Snagging

- A post-tender evaluation meeting took the form of an interview between key people with a number of contracting organisations still involved.  For Bovis the Executive (Colin Small), the Project Manager, Services Manager and Commercial Manager attended.  This is usual for this type of job and an agenda for such a meeting could be:-

- Introduction to Company (Brief)

- Introduction to Team (Previous experience)

- Programme / Methods (Project Manager)

- Maintenance of, and installation of store Services (Services Manager)

- Conclusions, followed by a

- Question and Answer session relating to ‘key areas’ of concern

- The decision as to who has won the job is usually provided within a few days.

- Selection of team

- Teamwork and co-operation is required at a number of levels within the relationship, strategic level, management level, operational (sub-contractor) level.  When forming any construction team there is usually a high level of opportunities for selection at the management and operational levels.

- People and organisations are selected who appear comfortable with each other and would be able to work together.  Contractors were used in the main, who have worked successfully in the past for Bovis or M&S.  It was stated that most client’s operate in this manner today.

- Specific sub-contractor selection criteria which were mentioned included:-

- levels of expertise

- ‘tried and tested’, based upon past performance in terms of

- financial performance

- quality

- safety

- programme

- Also, Bovis maintain an electronic database of sub-contractors which contains information regarding their previous performance on Bovis projects.  This resource is supported by personal knowledge of these organisations which naturally exists within the management staff and recommendations and references can also be passed on by word of mouth within the organisation if particular individuals have not worked with specific organisations.

- It was also stated (AT) that a critical requirement of a sub-contracting organisation is that they have a good site / project based manager.  It is good practice to interview this person prior to any engagement to acquire a ‘feel’ of their nature.  This is important as it is these people who Bovis will be working with and communicating with.  An important question to ask is, Can you work with these people?

- Construction

- The aim for M&S Bolton, indeed all M&S jobs is a ‘defects free’ job.  A worthy aim as this provides a better outcome for all parties (Construction Team including Management Contractor and Sub-contractors, Design Team, M&S, customers) as there is no need to go back and carry out repeat work.  The reality is that this is a difficult goal to achieve.  Bovis are managing a process and their job is to manage, control and motivate people and organisations.  On this job there were approximately 35 work packages of which about a quarter could be considered as ‘key’ players.  These critical packages were identified as follows:-

- General Builder

- Mechanical

- Electrical

- Sprinklers

- Refrigeration

- Ceilings

- Shopfitting

- Steelwork

- Roofwork

In conjunction to this large number of participants the job was extremely complex with access to the building restricted due to its town centre location (plan would be useful to illustrate this).

Some enabling works started early December although the bulk of the job did not get going until January (8th) after the Christmas and new Year peaks.  A key concern of M&S and Bovis was for the separation of construction activities from the rest of the store including customers and staff and for their safety.  The building must look like a store rather than a building site.

Construction Progress - the time of the year was a key element in this.  It is important to consider project start time and the types of work which are underway - lessons for future practice.  In the Bolton case, major work was being conducted on the roof in January / February which is not a good time to be working there for a town at the foot of the Pennines.

Programme Planning - this project also entailed the planning of two programmes (referred to as 200% planning) in an occupied and operational building.  These programmes were for day and night which led to a process of reacting to previous nights activities, plan today, plan next night.  Unforeseen night-time or day-time activities could create problems and there was a need to continually re-assess and refine programmes.  In conjunction with this daily programming there was also a need to continually monitor and refine medium and long term programmes as construction progressed.

The programme was also very tight with little float where strategic operations such as refrigeration installation, lift installation and escalator installation are critical to maintain the smooth operation of the store.  The fact that virtually all weekends were worked emphasises this (originally only an approximate 40-60% were anticipated as being required).

Also, Bovis were successful in providing Marks and Spencer with the benefits of additional and refurbished floorspace on specific agreed dates.  Details:-

Stockroom			24/6/96

Staff Quarters			15/7/96

Ground Floor Sales		23/9/96

1st Floor Sales			14/10/96

2nd Floor Sales		14/10/96

3rd Floor Sales		7/10/96

Complexity:-

- access very difficult

- number of workfaces operational at any one time

- unforeseen programming and planning

- This emphasises the importance of communication links with the store, the need to keep them informed about what is happening.  Sally Martin was the key link with weekly formal meetings with key members of the M&S store team, allied to frequent interactions on a daily basis relating to construction activities and progress.  The responsibility for Bovis is to manage store expectations so they know what they could expect to happen.

- Informal team building exercises such as ten-pin bowling and social evenings were a part of the construction process though not as frequent as on other projects.

- The store was completed and opened in the first week of November.

- Post Construction

- A post-contract review was undertaken with a structured agenda considering scope of works and to provide ratings for key parties (M&S / Consultants / Contractor / Sub-Contractors).

- Also corporate thinking between Bovis and M&S was embodied in a seminar held at Harrow fronted by Nick Penny, M&S.  In light of recently completed jobs (Newcastle, York, Bath, Crewe, Wigan) and to consider workload peaks and troughs with the importance of Christmas and Easter to a major retail client.

- Bovis policy on M&S projects is for the Project Manager to provide a summary report on each project relating to specific project performance (see Appendix 1).

- 4.0	Project Review

- The project was completed successfully although there were a number of design ‘problems’ and other ‘niggles’ relating to money.  At times friction existed between Design Team members due to inadequate surveys, building control issues and basic works co-ordination.  Similar problems to these tend to be industry wide but are currently compounded by fixed prices which offers limited scope for resolving problems, costs tend to be passed on and this can seriously affect programme.  The working relationship between the design team and Bovis at the operational level were very good throughout the project.

- M&S is a ‘professional’ client who like tried and tested methods and solutions and with operational stores their emphasis is upon safety, cleanliness, general appearance, signage and noise levels.

- The design was novated ‘warts and all’ and all the risk lay with Bovis.

- Key Issues

- As identified in interviews with the Bovis and M&S project managers at a relatively early stage in the project, key issues were as follows:-

- design and subsequent variations

- quality

- programme

- cost

- safety

- communications

Further specific issues which were identified on the Bolton project were:-

- The need to manage complexity (due to building location and nature of the project)

- Controlling cost in this situation

- Maintaining a consistent team

- Completeness of design at the tender stage and the possible need for a design audit at the tender stage

- The extent of pre-construction surveys carried out

- The criticality of selecting the right sub-contractors

- Specification changes

- the importance of the post contract review and learning for future projects

A number of these issues are expanded in TA Bovis Performance Memo (appendix 1)

Suggestions for Improvement

Job Specific:-

- Totally removing asbestos ceiling tiles prior to starting main construction works

- Scaffolding the job in a traditional manner

- delivery and storage

- two stage tendering process would have helped to share the risk

- All of the above had an impact upon cost but the learning curve provides opportunities for other projects.

- Summary

- A key aspect of this job which created tension between parties was ‘complexity’ of the solution and also the complex programming which this involved due to specifics of the job and access problems. Job specifics created a situation with lots of ‘workfaces’ which presented co-ordination difficulties for M&S storeteam, sub-contractors and the main contractor.

- Problem areas were money and design and it was stated that M&S now appreciate that the design was not complete when the job was let (the Tender Process was a ‘single stage lump sum’).  This is a recognised problem with ‘cut and carve’ town centre jobs.  Experience from M&S Bolton has led to subsequent jobs following a two stage tendering process including provisional sums in the lump sum and for elements of negotiation in the process.  Other procurement routes also being pursued by Marks and Spencer include Management Contracting and negotiated 2 stage lump sum contracts

- 5.0	General Comments

- Different jobs will have different critical elements depending upon job specifics but these will always related to cost and programme in some way.  This is due to the nature of the clients business i.e. retail.

- M&S view Bovis as a supplier but they are different to other suppliers as the majority of their product is not ‘built in a factory under controlled conditions in a repetitious manner’ (AT).  Also, Bovis provide a management service of a process which is currently fragmented.  Opportunities for greater levels of standardization of both construction products and the process will be offered with new build and to a lessor extent with ‘cut and carve’ projects.

- Procurement Policy

- Marks and Spencer procurement policy differs according to specifics of job and are happy to use a range of procurement routes depending upon which is appropriate for each job:-

- Management Contracting

- Lump Sum (Single stage / Two Stage)

- Negotiation

This flexible approach to procurement is a benefit of developed relationships between organisations and is essential in a business environment which increasingly requires adaptability.  Lessons from M&S Bolton are already filtering into M&S policy as other projects are being procured by different routes as mentioned above and the specific route depends upon Marks and Spencer requirements and the type of project.

Industry Problems

A problem faced by the construction industry is a skill-shortage amongst operatives.  This can be related to the boom / bust nature of the industry and how it follows the economic cycle quite closely, also training is the first budget which is cut when firms are trying to cut costs and there is also a problem due to the lack of directly employed labour at work on construction sites.  An example of this on M&S Bolton was with the ceiling fixers who had suffered in this respect and where the lack of skilled craftsmen impacted upon the cost and programme of the project, albeit the issue had been resolved before completion.