Adversaries or Partners? IMI EPSRC Research Programme

University of Salford

Interview ‘Summary’ Report

Date: 		9th February 1996

Interviewee: 	Charlie Stabler, Rigby & Partners, Structural Engineers

Location: 	Rigby & Partners, Chorley

Interviewer: 	Stephen Allen

CONTENTS

- Personal Background

- Project Summary

- Introduction

- Story of Project

- Pre-Construction Phase

- Construction Phase

- Post Construction Phase

- General Comments on Partnering

- Key Factors

- Suggestions for Improvement

Personal Background

Charlie graduated from Liverpool University in 1983 and joined Bingham & Cotterell Structural Engineers, St. Helens working on BNFL projects. In 1989 he joined Rigby & Partners and has been involved with Northern Foods on numerous projects.

Summary of Rigby & Partners Project Involvement

Some 12 months before construction works started on site, Rigby & Partners carried out feasibility studies and site investigations for Northern Foods and produced a report with certain recommendations. Subsequently NF’s decided to progress with the project. Once this decision was made various scheme designs were developed, on the basis of which Bovis were able to produce an initial cost-plan. Following this, detailed design was carried out on a ‘just-in-time’ basis before construction works were tendered to an agreed programme. During construction Rigby & Partners responsibilities were to monitor the progress and quality of the works, to assist in the control of variations and advise on payments and the agreement of final accounts for the works.

Introduction

Rigby & Partners and Northern Foods had a long established relationship of 20 years, and Rigby’s did ‘99%’ of all structural design work for NF’s. At least 15 major projects had been completed with London Colney being the most recent. NF’s were acknowledged as market leaders in the production of ‘state of the art’ buildings for the food processing industry and as a client know what they want. It was stated that in terms of the ‘partnership’ and successful completed projects this was the worst one to examine as this is the job where the ‘wheels fell off’. This breakdown was considered to be at a ‘personal’ level rather than a ‘company’ level (on a current project involving Rigby’s and Bovis nobody from Bovis would talk to Charlie for 6 months - this situation is now happily returning to normality ). Upon reflection it was stated that this was probably the best project to examine for exactly that reason. Initially the project was considered a very simple job but it turned out vastly more complicated due to external works problems.

Story of Project

Pre-Construction Phase

It was stated that the architects had been involved with the potential redevelopment of this site for years, but Rigby’s involvement began with a Feasibitity Study, comprising investigations of the site, existing buildings, ground conditions and some land surveying work, 12 months before the eventual start on site date. The basic problem facing Northern Foods at this point in time (1992) was, ‘is it worth purchasing the site for £20 million and then developing it?’. The existing building was currently being rented from the original owners, however NF’s needed to expand the capacity of the facility but the then owners could not fund the extension. As mentioned problems which were faced related to:-

- existing structure

- remedial works

- ground problems

- Rigby’s work constituted an investigation into these problems and offering advise to NF’s upon whether they should proceed with the proposed purchase and development.

- Existing Structure and Remedial Works

- The existing structure had been built in 1977 by Wimpey Construction but had a history of maintenance problems.

- Ground Problems

- The facility was on the site of an old tip with chalk deposits and had previously been the location for both a gravel works and chemical works (Harpic Factory). The pit had been filled with ‘Harpic’ which led to chemical reactions and settlement problems.

- The outcome to this feasibility stage was the identification that the building was relatively simple but the ground was not. With this information NF’s had to decide whether they were prepared to proceed or not. They decided they would and needed to source capital to buy the building and the estate. Once this was established and finalised the consultants and architects within the team alike felt, ‘yes, we’ve got a job, - let’s do it!’.

- So, once it was decided that the project would go ahead various ‘scheme’ designs were put together by the architect and Rigby’s. On the basis of these Bovis said, ‘We’ll build you this for £5 million, guaranteed maximum price (GMP)’. This initial cost-plan was put together on the basis of the ‘schemes’ which presented no more than ideas as to how the clients brief could be met. It was felt that this was facilitated through the established relationship and the understanding between parties which existed.

- Construction Phase

- Work on site started with only 1 drawing agreed, the ‘site-strip’. Work commenced very much with a ‘rolling programme’ where detailed design was performed on a ‘just-in-time’ basis from an on-site porta-cabin equipped with a drawing board. ‘Just-in-time’ drawings were produced for each tender package [Figure 1] and Rigby’s worked alongside Bovis to produce information. Bovis attempted to controll both design and cost, which developed into an iterative process to keep on top of costs (due to GMP). This committment to ‘just-in-time’ working was an important element of the ‘partnership’ and team-working, and is beneficial when programmes are tight or fast-track. This approach can be contrasted favourably to other more ‘traditional’ approaches where the design is completed before contracts are let.

- Rigby’s provided the sub-contractor with ‘information’ but other than this there was no relationship between Rigby’s and the sub-contractors. Bovis’ responsibility was to manage the process and deal with any problems / conflict which arose. During the construction phase a two way communiction process was in operation between Bovis and Rigby’s. The procedure for information / site queries was as follows:-

- subcontractor----Bovis----Rigby’s----Bovis----subcontractor

- This ‘chain of information’ worked well and as the sub-contractors were contracted to Bovis it was felt to be right that they had no contact with Rigby’s.

- The steelwork package was different. This package was not tendered and nominated suppliers and contractors were used in the form of Wards. Rigby’s talked directly with these contractors and through a process of negotiation a better price was agreed. (Wards work regularly with Rigby’s and were the steelwork contractors at London Colney, Sun Valley and Middlemarch).

- Throughout the construction phase various tensions and conflict arose and whilst it is difficult to pinpoint the exact cause of these, various factors contributed to the situation:-

- Guaranteed Maximum Price

- Programmes

- Contractor Capabilities

- Guaranteed Maximum Price

- Guaranteeing the price from an early date, based upon ‘scheme’ designs is difficult and if subsequent problems arise the only way to achieve the GMP may be by ‘compromising’. (These ‘compromises’ may be in terms of value-engineering or through fitness-for-purpose design but can lead to controversies or differences of opinions between stakeholders which create tension in the relationship). Also, due to the willingness of the Architect and NF’s site based Project Manager (Keith Bingham) to find fault with various aspects of the project which required remedial works, impacting upon project costs, the relationship was affected.

- [The project was undertaken with a ‘novated’ architect who had planning permission to extend the property for the original owners, and NF’s decided to go with them. They had never worked within the ‘partnership’ before and would never again!]

- Programme

- Conflict also arose due to the programme which was felt to be ‘tight’. An example of a problem associated with programming was the external concrete ‘slabs’ for the loading bays and delivery yards. Early work ‘in-situ’ turned out to be defective, Peter Goldsmith (Bovis PM) wanted to leave leave this in initially and take out at a later date so as, (a) not to lose momentum on the programme, (b) not to hit the sub-contractor early on and, (c) lose face reducing site morale. The slabs were condemned and had to be taken out and the programme was affected. Bovis wanted to ‘compromise’, the structural engineer didn’t. The problem as far as Bovis was concerned was, ‘have we got time to take remedial action, or do we say fitness-for-purpose?’. Bovis were responsible for managing programmes and do not build anything themselves, everything is sub-contracted and they must ensure that deadlines are met for following trades. The client is working to a particular date to be producing food products or to provide additional warehousing and at the end of the day it is this which matters. The feeling was the construction side of this process was squeezed harder than plant installation and the production run. However it can be seen that programme conflicts can seriously affect established relationships.

- Sub-Contractors Capability

- The capabiltiy of sub-contractors in meeting programme deadlines and reaching quality standards of workmanship are essential for a co-hesive and successful project.

- All three of the above factors cost, timing and capability are closely related and one will affect the other. A ‘ripples in a pond’ analagy was used to show that the action of an individual person / stakeholder can affect other people and the project as a whole.

- During the construction phase it was felt that an important factor was the project location, in a relatively ‘new’ region for NF’s. Charlie stated that he was living in a hotel with various sub-contractors, steel-erectors, electricians and roofing contractors which created an opportunity for an off-site social life and informal team-building activities. Potentially this created a problem situation where everybody is ‘too close’ and could not ‘escape’ from the project at the end of the day. Also, Charlie thought that it was Peter Goldsmith’s first job away from home despite his experience and with Keith Bingham’s permanent site presence he usurped Peter on the social side through the organisation of pub crawls, treasure hunts and other activities.

- Post Construction Phase

- It was noted that no formal end of contract celebration occurred on this project. A rare occurrence in Charlie’s construction experience.

- General Comments on Partnering

- An interesting observation related to the level of activity within the partnership. Three distinct levels within the relationship were identified:-

- strategic

- tactical

- operational

- Strategic - this is probably the key to the continued partnering arrangements as it is at this level that relationships are historical and well established with memories of successful projects and developed understanding and a sharing of values, norms and standards. Cultural alignment? People at this level are directors (Dennis Bate, Cliff Brian,?) and senior managers (Brearly, Worthing). Long-term view.

- Tactical - this level of the relationship revolves around the management and organisation of the project. Senior managers and project managers and co-ordinators are involved in the interactions. Medium-term view.

- Operational - this level of the relationship is the interaction between the managers and the people doing the work on a day-to-day basis. Project (short-term) view.

- The feeling was that there was scope for disagreement / disputes at both tactical and operational levels and as long as this was not too traumatic the relationship is likely to continue due to importance of the strategic level within the relationship.

- Key Factors

- Key factors for successful partnering identified in this interview can be identified as follows:-

- developing team-working

- openness and honesty

- dispute resolution

- personality clashes

- realistic programmes

- accurate cost-planning

- identification of appropriate levels within relationship for problems to be resolved

Good Practice / Suggestions for Improvement

Past experience has shown that on-site working (for structural engineer but maybe not client), no drawings / records at head office, gives an immediacy and ability to clarify problems within the project environment. Also, the permanent on-site arrangement allows for full integration into the project team. However, this is only possible if fees allow.