## Best Practice for Partnering in Construction

Rachel Cooper, John Hinks, Stephen Allen, Stuart Carmichael

University of Salford

Hadyn Worthing

Bovis Construction

Abstract

# This paper details the initial findings from a collaborative research project being undertaken between the University of Salford and Bovis construction.  The paper presents the background to the research project, research aims and objectives and why Bovis were an appropriate organisation for the research.  A speculative model of partnering relationships in construction is presented.  This model is characterised by the length of the relationship; the nature of the relationship in terms of attitudes and behaviour of stakeholders; and the form which any contractual agreements take.

A case study of Bovis and a client with whom they have a long term relationship is used to illustrate some aspects of the model highlighting key areas of concern.  Specific lessons which were learnt from a project within this relationship are highlighted and in conjunction with other case studies general key issues are identified. These issues provide a focus for developing best practice for partnering in construction and the paper concludes by identifying current and future research on the project.

# keywords Collaborative working, long-term relationships, case-study research.

# 1.0 Research Background

# 1.1 Aims of Study

## The research project has three principal aims, which are to:

## Analyse the design and operation of ‘partnering’ arrangements in the design and construction process, and to identify the criteria upon which successful partnering between clients and contractors, and contractors and suppliers depend.

## Identify the costs and benefits of partnering compared with a ‘traditional’ adversarial approach in construction.

## Develop best practice guidelines to aid client, contracting and supplier companies wishing to design and operate partnering relationships effectively, supported by training materials for construction management courses.

## Also an essential part of the project, which forms part of the EPSRC Innovative Manufacturing Initiative (IMI), was to compare construction partnering with implemented policy and practice from the manufacturing industry.

# 1.2 Research Method

### Preliminary Interviews have been undertaken  in order to provide a general overview of attitudes and experiences regarding partnering. Case studies of Bovis Construction, investigating a variety of projects ranging from retail refurbishment projects, large scale retail parks and industrial developments are currently being undertaken. Mini case studies in other industry sectors such as retail, aerospace & construction component manufacturing are also being conducted to facilitate cross industry comparison.

# 1.3 Why Bovis?

Bovis are reputed to have a culture and tradition of non-adversarial relationships with customers and suppliers. They are committed to TQM and Continuous Improvement challenging accepted principles and practices within the industry. Also, the relationship between Bovis and Marks and Spencer in the 1930's became the first real modern partnership in construction.

Bovis has consistently demonstrated its commitment to focus upon the needs of individual customers. The company has always been unique in its approach to construction, as demonstrated by the Bovis Fee System which was developed in 1927 as a radical departure from the lump sum tendering which is still the standard industry procurement route and a major contributory factor in adversarial relationships. The relationship that subsequently evolved with Marks and Spencer in the 1930's became the first real modern partnership in construction, a philosophy which Bovis has successfully extended to other client companies. Meanwhile, Bovis remains Marks and Spencer's largest construction services supplier. Bovis also believes in the importance of partnering down the supply chain, and has a policy of opening its training programmes to both customer and supplier companies.

Bovis has continued to sponsor and participate in research and activities to improve the construction industry, including projects with BISRIA which target design productivity improvements and clarification of design responsibilities. Bovis was also one of the first members of the CIRIA-managed Construction Productivity Network, which promotes and shares best practice with clients and contractors. Bovis was a significant contributor to the Latham report, and is an active participant in Working Group 11 - 30% reduction in real construction costs, which includes tradition of non-adversarial relationships with their customers and suppliers makes it uniquely placed to collaborate in research into the production of construction industry best practice guidelines for partnering. In 1994 Bovis became a founder member of the Reading Construction Forum, a group consisting of leading client, contractor, design team and specialist contractor companies. The Forum exists to promote quality, innovation and change, through research, best practice and liaison between industry and Government.

2.0 Speculative Partnering Model

This section will present an initial speculative model of the types of project relationships in construction which our research to date has identified.  A commentary upon the Bovis approach to partnering and to developing relationships with clients, sub-contractors and suppliers to the industry is then included.  This provides some contextual background for the case study which is presented.

2.1 The Model

The research to date has seen the development of a speculative model of partnering between clients and contractors in construction.  The initial concept was based upon two seemingly polar approaches to contracting; contracting based upon a formal ‘agreement’ (i.e. a contract) which determines the nature of relationships and allocation of risk; and contracting based upon sympathetic attitude between ‘partners’, characterised by collaborative, open and trusting behaviour.  As data was collected it became apparent that the situation in practice was far more complex for a number of reason including time horizons of clients and projects, individuals involved, selection processes and project specifics.  This developing and speculative partnering model is shown below:

The basic premise of the model is that each option, (1,2,3,4), represents different types of organisational relationships on construction sites.  Key issues in identifying the ‘type’ of each project seems to be the nature of the client and their particular project requirements.  This in turn effects issues such as the process of identifying the clients brief, team selection, team building, managing the construction process and project performance evaluation.  A brief description of each of the above positions is as follows:

1 - This in a sense relates to any construction project.  The complex nature of modern construction projects requires organisations to develop close working relationships and trust is essential.  This is usually project specific and any ‘partnering’ which takes place occurs in an ‘ad-hoc’ manner and may occur between client, contractor or suppliers.  No formal ‘partnering’ activities usually take place (for example, partnering workshops, team building exercises, developing a partnering charter).

2 - These types of projects see definite formal attempts to develop ‘partnering’ attitudes and behaviours on site.  Essentially short-term in nature (project specific), although there may be a commitment for stakeholders to undertake future work together.

3 - Longer term relationship, although here the client adopts rigorous selection and evaluation procedures of contractors carrying out projects.  Relatively large client spend on construction activities which leads to client developing rigorous management procedures (selection and review for instance) to ensure value for money.  National retailers and large commercial developers (e.g. BAA) fit into this category.

4 - Long term but not as formal as 3, with maybe a smaller construction spend by the client who are confident in using only one or two major construction companies as and when they have a particular construction need.

### The research with Bovis has been illuminating in the fact that a range of approaches have been identified within Bovis in how to respond effectively to the needs of specific clients and project types; the approach is tailored to the specific situation.  A little more shall now be said of this flexibility.

2.1 The Bovis approach to Partnering

Bovis operate with the policy that the Clients hold the key to successful projects, a ‘client-centred philosophy’.  Sir Michael Latham understood that clients are at the ‘core of the process’ and in Constructing the Team refers to them as the ‘driving force’.  Bovis feel that it is only by clients and the industry working together will performance and productivity improvements be achieved.  Partnership is a Client driven process giving working benefits to both the contractor and the Client.  It requires the ‘customer power’ of the client to lead the way to real partnership, and for contractors with the appropriate culture and people to match their progressive approach to construction procurement.

Bovis has many other long-standing relationships with Clients and identifying and meeting Clients’ needs have always been a priority.  Listening to these needs led to the introduction of Bovis Effectiveness in 1991 which was launched with three key targets:-

- reducing construction costs by 30%

- increasing staff productivity by 100%

- improving customer satisfaction

These three aims have been at the forefront of efforts to lead major change in the UK construction industry, by working in partnership with both customers and suppliers.  It was recognised that the cost and productivity targets set by Bovis Effectiveness would require a radical new way of doing business: new relationships, new cultures, new contracts and new attitudes. The oil and petro-chemical industries provided models which were investigated as examples of a non-adversarial approach to working relationships which aimed for continuous improvement of business performance.

It is worth identifying one case study in order to illustrate the Bovis approach to partnering and to illustrate a particular instance of ‘client focus’.  This will also help to identify the successes of such a collaborative approach.

# 3.0 Case Study

# 3.1 Background

The client in this project, Northern Foods plc, is the UK’s leading dairy company and a major producer of prepared foods.  They focus on product areas where they have substantial market shares and strong customer relationships. The company places a consistent emphasis on high quality, excellent service and product innovation.  These values are combined with continuous investment in improved facilities and technology to ensure low production costs.  Today it is the UK’s most broadly-based fresh food manufacturer with over 25000 people employed in 50+ autonomous business units across the UK with a turnover of around £2 billion.

Northern Foods believe that there are several factors which account for success:-

- concentrating on the right customers

- concentrating on the right product areas

- focusing on product innovation and development

- having a commitment to safety and hygiene

- investing in productivity and efficiency

- making relevant acquisitions

Of the above factors in the success of Northern perhaps the fifth one, investing in productivity and efficiency - the fact that Northern has never been shy about putting money into new facilities or into upgrading existing ones is critical.  This factor combined with a positive attitude towards acquisitions and amalgamations results in a demand for new improved facilities on a regular basis.  It is likely that this is a key aspect in the development of a long term relationship between Northern Foods and an organisation from the construction industry, Bovis Construction.  Bovis has an evolving process of continuous improvement working with Clients to improve the quality, costs and programmes of construction projects.  Prior to the start of the London Colney project key executives from both companies went on a joint study tour of the USA to benchmark best practice in constructing similar facilities in the States.

3.2 Project Overview

The project was tendered on a 2 stage lump sum guaranteed maximum price (as a requirement of the funders) in the region of £6million. The building was an extension to an existing Distribution Centre for Northern Foods Transport in St. Albans and the project entailed the provision of a new warehouse and offices, modifications to the existing warehouse, construction of a new lorry park and a new recreation field and Section 106 road works.  The programme for construction was approximately at 12 months.  This project was the thirteenth major project in 16 years in the Bovis / NF relationship.

Allowing that on paper, this should have been relatively more straightforward it presented quite a different challenge to the previous contracts.   Different Design teams had been used on previous projects. The architects for example had been used on the majority of the previous process related projects (Riverside Bakery, Rawmarsh, Fenland Foods, Pennine Foods, Gunstones Bakery, Bowyers and Palethorpes) and took on responsibility for design, layout and function.  The structural engineers were also a common ‘theme’ in most of NF’s food processing work. The majority of sub-contractors finally selected had worked with the Bovis Project Manager and other members of the team previously.

The project saw the continuation of the Continuous Improvement philosophy from previous projects embodied in the Bovis Effectiveness Initiative and this project benefited from the implementation of the effectiveness initiative.  Figure 2 illustrates the ‘effectiveness’ focus on the London Colney project:

Figure 2: Project ‘Effectiveness’ Focus

3.3 Project Story: A Collaborative Approach

The successful implementation of “Bovis Effectiveness’ in order to deliver the project on time and within budget had to be impressed to all those involved on the project. The development of effective relationships and efficient communication were highly important in making people accept the Bovis Effectiveness Initiative, which in essence challenges existing design methods and working practices.  The culture of the project was non-adversarial based upon mutual respect; a professional respect for other members of the team.  A flexible ‘open’ management style was adopted with a hands on approach and early involvement in decision making. The attitude adopted on this project has been termed ‘culture by consensus’ where existing solutions were challenged, team members were challenged to hold no pre-conceptions and innovative ideas were deliberately sought I solving problems, reducing wasted time and avoiding duplication of effort.  The following section will illustrate how effective relationships were nurtured throughout the project life focusing upon key activities and will identify the benefits of such a collaborative approach.

3.3.1 Pre-Construction Phase

Critical activities prior to the commencement of construction works were identified as (a) the tendering process and contractor selection and (b) the team building exercise.

Tendering and Contractor Selection

The selection procedure started at the same time as the site work commenced and the work packages were tendered on a rolling programme as construction work progressed. Each package was tendered to approximately 6 contractors and although the tendering process operated in a tough competitive environment the sub-contractors selected had worked successfully with Bovis in the past. The organisations had proven capability and established credentials and this process ensured a high level of technical capability.

Tender lists for each work package were developed following discussions with the whole project team, and, where necessary, an interview of potential contractors.  All team members were encouraged to input suggestions and finally agree the list.  Also, the M & E contractors had both worked with the teams previously and understood the philosophy necessary for pro-active involvement and alternative cost-effective solutions.

The tendering process operated within a framework of open-tender bids and the client could have been present at the opening of the tender submissions if he had wished to be.  The purpose of this was to establish trust and openness as a central idea within the contract at an early stage.  in fact the whole management and cost system was ‘open’ to all the members of the Project Team and all were actively encouraged to be pro-active and look for ideas and cost savings.

Team-Building Exercise

Once the sub-contractors had been selected measures were taken to establish and develop lines of communication.   A general ‘team-working’ meeting was carried out with all sub-contractors.   Also, a formal ‘partnering’ or ‘team-building’ day was held.  This was staged at a time to ensure that key contractors were available following the procurement process.  Sub-contractors, professional design team and contractors representatives were all present with 22 delegates in total (NFT end-users, NFT Project Managers, all design consultants, key sub-contractors, Bovis Construction team), and the post-workshop analysis showed a very positive response.

A project logo was developed to display around the site focusing upon the three key issues of innovation, quality and teamwork.  This logo was developed rather than a mission statement as the team felt that is was a more appropriate way to express the desired message (see figure 3).

Figure 3: Project logo

3.3.2 Construction Phase

Construction work occurred in parallel with the fine-tuning and completion of the design of the building works (July - November 1993) and the thrust of the team was to ‘challenge solutions’ in order to achieve a more effective job.  Regular review meetings took place focusing upon cost, quality and programme and seeking continuous improvement in these areas.  In these meetings opportunities were identified and proposals were evaluated and developed and successful proposals were implemented without delay.  Whilst this process was successful in getting things done it was a tough period for relationships due to the ‘face to face’ nature of developing proposals.

Meetings

Once the sub-contractors had been selected the first step before starting their works on site was to attend an ‘Initial Pre-Construction Meeting’ to establish expectations, lines of communication and to identify problems / bottlenecks prior to the contractor commencing on site and to give support and direction to enable the most effective working.  This helps to establish positive links before inevitable construction ‘problems’ started on site, and to establish the standards of behaviour expected of people working on a Bovis site.  The more effective contractors are the keener their bids become on future projects, all part of a continuous improvement cycle.  The meetings are ‘open’ and all members of the project team are encouraged to be present.  Key aspects of this meeting included personnel, scope of work, reporting procedures, programme, workmanship and quality, safety, protection and site cleanliness.

Generally ‘Trade Contractor Progress Meetings’ were held on a two weekly cycle. These were chaired by the Bovis Project Manager and these meetings regularly looked for further cost savings, alternative ways of doing things, either during the pre-construction or construction stages.

‘Weekly Safety and Co-ordination Meetings’ were also held, with the site supervisors of the relevant sub-contractors and chaired by the Bovis Construction Manager. Again these meetings are ‘open’ and members of the Project team attend when there are specific issues, constraints or problems to discuss.

These activities were considered to be ‘General Good Practice’ to be observed on all sites, not just within ‘partnering’ arrangements but it is worth noting the importance of face to face meeting and the presence of the design team on site to help communications.  This primarily site based team permitted the development of close relationships and encourages everyone to contribute to the process.  A little more shall be said now about this ‘teamworking’.

Team-working

The Effectiveness Initiative, incorporating team working, created high expectations for this particular project.  Team building was set to be a continuing process with champions allocated to promote development in specific areas reached by consensus at the initial ‘Team Building Day’.  On this project, due to the fact that people were living together there was a problem that people may get too ‘close’, and this familiarity may compromise professionalism.  Most team members used the same hotel and there was a considerable amount of rich, informal discussions during the evenings which Bovis feel contributed in some way to the eventual cost savings and achievement of milestones during the programme.  Also, the Clients PM, was on-site for 3-4 days / week and he shared a hotel with other ‘team’ members. This provided an opportunity for people to ‘gel’ if they got involved in the various activities which were taking place.  This helped to establish and develop teamworking.  The structural engineer stated that he was living in a hotel with various sub-contractors, steel-erectors, electricians and roofing contractors which created an opportunity for an off-site social life and informal team-building activities.  Social activities on site were good with the organisation of social evenings, treasure hunts and other activities which helped develop the sense of togetherness and team-working.

When working on construction projects there is a need to appreciate others, in particular their strengths and weaknesses, to maximise output on the project.   Team-working is essential but the importance of ‘chemical-selectivity’ was stressed by the architect and the problem of forcing the development of ‘teams’.  The architect expressed the opinion that this was a naturally occurring phenomenon which you can do very little about although bringing people together in a ‘non-critical’ situation seems like a good idea.  So, the concept of team-working is good but how you go about setting it up is very important and over-familiarity can be a danger.

3.3.3 Post Construction Phase

The Project Review

Bovis and NF have a de-brief on all projects and without exception review the performance on the relevant project and try to identify better ways of conducting business in the future.  Specific questions which are asked at these meetings are as follows:

- What did we set out to achieve?

- What did we achieve?

- What worked for us?

- Where could we have done better?

- What did you personally get from the project?

- What didn’t you get?

- What is our wish list for the next project?

This process is definitely good practice but identifies a general problem within an industry, where people have to move on to the next job, as new projects arise, and there appears little time or money available to review projects which would provide a formal opportunity to learn lessons.  This task must be considered an essential element of the continuous improvement ‘cycle’.

The project was successful and in some ways there was a good ‘construction’ team, though a few problems surfaced during the project duration.  The final product, a regional distribution centre (RDC), became operational 3 months earlier than had been originally anticipated despite an increase in scope and additional works; considerable cost savings were established during the course of the project (see figure 4) and throughout the project over specification was reduced which enabled the Client to buy more facilities from a ‘wish list’ resulting in a more effective business operation; the RDC was constructed to a good quality and specifications could have been further reduced and still achieved ‘institutional standards’ and compares favourably with industry cost benchmarks (see figure 5).  The project was also a joint winner of the Bovis annual safety award.

Figure 4: Cost Reporting Milestones

Figure 5: Cost Benchmarks from Previous Projects

4.0 Discussion

This section provides a discussion of the outcomes of the case study, identifies opportunities for continuous improvement and briefly contrasts the process identified in this construction case study with manufacturing.

4.1 Case Study Review

In light of the Latham report, the London Colney can be seen to be addressing a number of issues which were raised in a practical manner.  In particular the London Colney project emphasised fair dealings between parties, teamwork based upon shared financial motivations and a general problem solving culture with no intent to use the contract.  Also, the project was lead by the Clients representative Project Manager and the emphasis very definitely was upon a client driven innovative culture.

A potential barrier to partnering which was clearly identified during the conduct of this case-study was the differing perspectives or viewpoints, and also the cultures and traditions of the participants.  This conflict can creep into the project based upon individual (personality clashes, differing philosophy), organisational (designers and builders for example) or institutional (RIBA, RICS..) values.  Issues where these tend to manifest will relate to cost, time, and quality, for example the over specification of design.

On a project such as London Colney where an innovative approach to the construction of the facility was being adopted, ‘traditional’ viewpoints became a barrier to the new way of working and created frustrations.  This may or may not have been a useful ‘check’ on the process but illustrates the need for understanding of other team members in the pursuit of a smooth job.  Selection of team members was consistently highlighted as an area for development on future projects.  Good partnership allows things to be resolved and this is achieved through understanding and commitment to a common cause.  Key factors identified during the interviews and discussions which were considered to be critical in the development of successful partnering arrangements are as follows:-

- developing the spirit of team-working

- building relationships

- effective two way communications between ‘multiple’ stakeholders

- openness and honesty

- establishing trust

- maintaining trust and honesty (very difficult to establish, easy to lose)

- importance of individuals

- dealing with problem of personality clashes

- sub-contractor selection

- understanding roles & responsibilities

- understanding relative strength & weaknesses

- right first time philosophy

- realistic programmes

- accurate cost-planning

- identification of appropriate levels within relationship for problems to be resolved

- dispute resolution

The case-study identified a number of key factors and suggested areas where future improvements could be made.  In a sense these relate to a project-specific relationship, though the longer-term nature of this relationship means that additional benefits may accrue.  As the research continues these findings will be tested more rigorously and this case forms a useful benchmark for the project.

Levels of Partnering

An interesting observation related to the level of activity within the partnership. Distinct levels within the relationship were identified, the main levels being:-

- strategic

- operational

Strategic:  This is probably the key to the continued partnering arrangements and are critical for long term stability.  It is at this level that relationships are historical and well established with memories of successful projects and developed understanding and a sharing of values, norms and standards.  Key individuals at this level are directors and senior managers.

Operational : This level of the relationship revolves around the management and organisation of the project.  Senior managers and project managers and co-ordinators are involved in the interactions. Medium-term view.  This level also relates to the interaction between the managers and the operatives undertaking the work on a day-to-day basis.

The feeling was that there was scope for disagreement / disputes between these levels and as long as this was not too traumatic the relationship is likely to continue due to importance of the strategic level within the relationship.  These levels need more work in terms of the team building and the process by which they work. The process has to be right and efficient and effective communications absolutely essential.

4.2 Continuous Improvement Opportunities

With the emphasis on this project being ‘continuous improvement’ and ‘effectiveness’ what lessons can be learnt for when the next Bovis / Northern Foods job arises and implemented as a continuous improvement measure?  Specific issues or areas which provided benefits on this project include focused ‘set-up’ meetings as practised at London Colney, bringing together ‘interfacing’ trades to establish lines of communication; the employment of a ‘Client - centred’ Project Manager with relevant skills, experience and understanding of the clients values; on-site design offices are essential on similar projects to act as the interface between design completed at the Designers office and site demands.  The increased use of IT systems this is now becoming the norm and gives an immediacy and ability to clarify problems within the project environment.  Also, defects were rectified as and when they occurred, rather than allowing them to accumulate.  The message here is to agree to sample room standards and stick with them.

Specific areas which could have improved the process on this job include an increased fee for the Cost Consultant’s to allow for improved cost-control of ‘design-development’. Related to this issue is the freezing of design as early as possible, and the involvement of the contractor at an earlier stage (maybe along the lines of Design and Build) to give advice upon ‘buildability’ and lead in times for programme purposes, and help to reduce over-design.  This led to the feeling that on this project that ’time was against the team’.   The team should have more time to evaluate costs and settle the design which earlier involvement would have provided.  There is also a feeling that there was a need to agree ‘cost-reporting’ system to client at an early stage and stick to it.  Clarification of ‘fitness-for-purpose’ at early stage would have reduced some confusion and this could then be related to the clients requirements when developing the specification.

General lessons which can be identified include the need to maintain rigorous sub-contractor selection criteria.  To identify clients and their requirements clearly (problem of multi-layered clients), and have clear guidance from the client what is being built at an early stage.  The research also identified a need to develop and use a form of building contract which protects everyone's interest.  Reducing layers of management, seek to simplify management structures and communication channels was considered beneficial and the Quality Management / Assurance System which Bovis were operating on this site was claimed to be second to none but the clients view is that these systems can act as a smoke screen behind which bad workmanship may occur.  The value and utility of such systems may need to be reconsidered.

The above provides an overview list of areas where future practice (and research) could offer tangible benefits to the construction process and particular parties involved and offers real opportunities for learning.

4.3 Comparative Work

Partnering has been used to describe a way of dealing with adversarialism between people and organisations by introducing shared objectives and long term collaboration in industrial projects. The term is used however with reference to a diverse number of different industry sectors which can have fundamentally different attributes. Cross sectoral comparison can be undertaken most effectively when industries have recognisable similarities. For example, although most manufacturing sectors design and produce fundamentally different things, most have comparable processes, relatively long term development periods and similar critical factors such as just in time supply, quality of design, innovation, production times and resource wastage issues. However when attempting to compare approaches of strategic collaboration to industry sectors outside manufacturing the identification of potential benefits becomes more difficult as the process becomes less comparable.

Nevertheless there are identifiable partnering criteria that have been shown to result in performance enhancements in the automotive industry and it is worth summarising these in order to illustrate the likely differences and similarities between partnering in  construction.

There is a consensus of opinion that collaborative strategies and techniques have played an important role in the streamlining of the automotive industry.  Previous research in this sector [Cooper and Leverick, 1995] shows that the same sorts of factors are important in manufacturing as in construction.  These include team building exercises, rigorous supplier selection processes, commitment and everyone buying into the goal. As in any collaborative business venture, trust was shown to be vital to the success of the relationship. There is great importance placed on resolving at the outset what is to be gained from the relationship such as:

- the form of the arrangement

- the choice of people

- how to assess the process

- how to maintain focus

- how to assure the relationship continues

Furthermore it is normal for one organisation to control the relationship usually being the most powerful organisation such as the assembler in the automotive industry. Indeed Kichiro Toyoda (as reported in Lamming, 1993), suggested this as far back as the 1940’s along with the following important factors in sub-contracting policy.

- Recognition of the specialist abilities of the supplier as crucially important

- Necessity of having some form of shared capital / financial tie to secure a relationship.

Research findings also show that the partnering relationships in manufacturing span over a much longer period of time. In a recent study of automotive supplier organisations it was found that the average relationship of a supplier with an automotive assembler is 21 years. On top of this 28% of supplier revenue on average was accounted for by a single customer and that 77% of a customers requirement was supplied by that supplier.

This certainly represents a marked difference to construction which has shorter project duration’s and a greater turnover of staff. It was found in the supplier study that relationships must be given time to develop and problems were found if personnel changed frequently. Staff turn over is therefore a major issue which must be addressed in any manufacturing or construction partnering policy.

Generally research findings suggest that partnering has gone further in manufacturing than in construction. Suppliers for example are aware that they must take on additional responsibilitiesFirst tier and in some circumstances second tier suppliers must take on responsibility for warranty in a partnering relationship. Previously, assemblers would take on this responsibility but they would be very prescriptive concerning the specification of materials and design of the component. The partnered approach in the automotive industry is to trust the suppliers expertise, which makes the process of supplier selection extremely important. The suppliers are also responsible for the management of their subcontractors, which removes considerable management burden form the main assembler. Furthermore the greater part of the reason for the partnered relationship is to improve the quality of both the product and the process of just-in-time supply and manufacture. The supplier is therefore expected to invest time and resources in research and development in order to improve their own competitiveness and hence the competitiveness of the assembler. A true partnered relationship in the automotive industry will see the assembler being actively involved in the research and development activities of the supplier where targets are set and progress monitored through bench marking procedures and open book policies. The development of such information systems which consist of formal monitoring, control and feedback procedures is critical to the long term success of the partnering arrangement. It is also what is at present considerably lacking in construction partnering.

4.4 Summary

Partnering in manufacturing has been utilised for a significant amount of time and has been a mainstream strategy tool for about 25 years. There is considerable awareness concerning the costs and benefits of setting up such arrangements and companies plan partnering strategies in fine detail to avoid possible penalties. The partnering arrangement is finely tailored to suit the particular organisations involved and is not seen as a universal solution. In construction there still seems to be the feeling that partnering is a panacea, the cure to all ills in construction. For partnering to be successful in construction there is a need to develop mutual understanding between parties.  This is an understanding of ‘requirements’ and of other ‘stakeholder’ positions.  For this to work the onus and responsibility is shared and does not lie solely with one party but this understanding must be client focused.  However the partnering arrangements do not seem to be planned as methodically or implemented as stringently as in manufacturing. The major factors for this can be summarised as follows:

	partnering new to industry & less well understood

	short term nature of industry

	high turn over of staff

	one off product

	Less identifiable lead partner

These factors can make the incentives for partnering less clear which profoundly affects the ability of parties to agree on a rigorous partnering procedure at the outset and this in turn can affect the ability of the parties to develop the control systems required to ensure its successful implementation.

Partnering therefore is usually a fundamentally different animal to its counterpart in manufacturing, being on the whole less formal and less well defined. Whether it will be utilised as extensively and successfully will depend upon whether it can also consistently provide identifiable performance improvements to the collaborating parties. The short term one-off nature of construction projects make this far more difficult to assess than for a more stable, long term, repetitive production process.  Broadly speaking, partnering in manufacturing can be seen to be more formal, leading to the development of  information control systems designed to manage the partnering arrangement over a certain period of time.

Although the research to date indicates that on the whole partnering in construction is not as sophisticated as in manufacturing for the reasons outlined above, the Northern Foods case identified certain performance improvements that can be attributed to the partnering policy on the project. The focused set up meetings, which integrated trades and Bovis management to establish lines of communication were an important improvement to the process, as were the on site design offices for all members of the design team which considerably improved communication and feedback times. Furthermore the employment of a ‘client-centred’ project manager with relevant skills, experience and understanding of clients values was essential to the successful implementation of a client led partnering arrangement. This enabled the project organisation to be modified from a more traditional situation to suit the particular project.  An example of this was the cost consultancy role being performed in house by the contractor which led to identifiable cost savings.

In manufacturing therefore, a continuous cycle of innovative product and process development is crucial to the competitiveness of collaborating organisations. Innovation can be seen as a result of good partnering in manufacturing and considerable effort is spent in structuring the partnering strategy to allow for effective collaboration between organisations for example R & D, design and production. The time scale of projects is enough to allow for monitoring (through bench marking and open book policies) and modification of the strategy as and when required. Townsend (1996) suggests that manufacturing uses a fixed process on a production line and the products move along it, whereas construction has a fixed product and the process moves. With this criticality of process in mind it is perhaps not surprising to find that the majority of identifiable improvements that are facilitated by construction partnering arrangements, can be attributed to innovations in the management of the process as illustrated by the NF case. Such improvements to the process which are afforded through partnering are extremely valid because in construction effective innovation of the product, i.e. the final building, requires manufacturing and construction organisations to work collaboratively with each other. In order for this to occur effectively the construction project organisation must be operating in a cohesive manner, aiming to attain identifiable and agreed objectives. Innovation of the product is therefore highly dependable on the efficiency of the process. The case illustrated here shows that partnering can potentially improve the process. It would be an exciting prospect if the same mechanisms can eventually improve product innovation through more effective collaboration with component supplier organisations.

References

Cooper, R.D. and Leverick, F. (1995) Supplier Role in Product Development: A study of the Automotive Industry  Final Report, University of Michigan’s Japan Technology Management.

Lamming, R. (1993) Beyond Partnership: Strategies for Innovation and Lean Supply  Prentice Hall.

Latham, M. (1994) Constructing the Team: Joint Review of Procurement and Contractual arrangements in the UK Construction Industry  London, HMSO.

Townsend, M. (1996) Learning from Japanese Construction. Workshop Report, Construction Productivity Network, CIRIA.