Adversaries or Partners? IMI EPSRC Research Programme

University of Salford

Interview ‘Summary’ Report: M&S Bolton

Date: 		19th December 1996

Interviewee: 	Sally Martin, Store Liason Manager, M&S, Bolton

Tel 01204 528 491

Fax 01204 398 068

Location: 	In-Store, Bolton

Interviewer: 	Stephen Allen

CONTENTS

1.0	Personal Background

2.0	Project Summary

3.0	Story of Project

Pre-Construction Phase

Construction Phase

Post Construction Phase

4.0	Project Review

Key Issues

5.0	General Comments

1.0	Personal Background

Sally previously worked in head office and moved to Bolton from the Preston Store.  Sally’s role at Bolton which was initially split between commercial management and dealing woth Bovis, developed into a full-time liaison role between Bovis Management, the construction team, the store team and customers.  Her main concern to keep both staff and customers informed and happy in relation to the disruption and upheaval associated with a major construction project.  The issues of concern and potential problems the M&S store team face are obviously different to those of the construction team.  This serves to illustrate the complex interaction of differing perspectives when reviewing a construction project and the need for excellent communications.

Communictions

Information exchange and keeping people informed were identified as key activities.  In-store communications was at the end of a complex information channel involving numerous parties who needed to provide and receive information which was accurate and timely.  Sally’s liaison role with Bovis fed into a liason with M&S staff with the aim being to communicate, to provide a physical pressence, to be ‘fun but informative’, to be visual and to effect a trickle down of information from the focus team.  There was also a need to follow up and review activities in a continuous evaluation process.

Roles and Responsibilities

Communicating to divisional team, and main contact with Ted Brown, Advertising, Baker Street developed ‘tin-tin’ men which decorated the screening to provide more pleasant environment and to inform customers that construction works were underway.

2.0	Project Summary

Multi-storey extension to existing store increasing retail space from 48000 - 68000 square feet.  Classic layout (details) with lingerie on the top floor.

3.0	Story of Project

Pre-Construction

When the development opportunity at Bolton became apparent a series of brainstorming and team building events occured in-house amongst senior management (Store manager, deputy, finance manager and personnel manager).  The aim of these events were to develop a strategy to cope with the building works and to minimise their impact.

The design of the Bolton store was signed off very early as complete (Summer 1995).  This created problems as the project developed and the nature of the existing building became apparant and requirements changed as they are want to do in the retail industry.

Construction

For M&S, and any other retailer, the year is characterised by a series of key events which provide good sales opportunities; Christmas, January Sales, Valentine’s Day, Easter, Mothers Day, Fathers Day, Back to school period.  In a 12 month contract it is inevitable that works and key dates will clash and this presents specific planning and programming objectives which it is necessary to work around.  It is likely to be in the contractors brief to avoid major disruption around these periods of time.

Programme

The original programme slipped for a variety of reasons; number of workfaces, adverse weather conditions and communications from head office.  Considering these complications the construction team did extremenly well to hand over only 1 week late.  As project progressed there was a need to continually ‘re-phase’ the programme to ensure target dates were met.

November - some enabling works were carried out but it was not until January when Bovis started work on site in earnest.  The tower crane went up in January and this was considered symbolic of the project starting.  Serious weather problems were experienced in January, February, and March which affected works.

| Date | Construction Activities | Problem Areas | Strategy to deal with specific problems |
| --- | --- | --- | --- |

The worst ‘pinch’point was when the screening to construct the scissor escalator, 2/3 way through the programme.

Teamworking

Essential to foster sense of ‘team’ amongst staff at periods which were stressful and frustrating.  The works seemed to continually impact upon the same people and it was necessary to take special attention of these staff.  The continual process of de-merchandising and then re-merchandising created tensions and frustrations for particular staff members who were regularly affected by the development.  Of approximately 200 staff, half were seriously affected particularly wines and foods due to the need to move full racks of wine and the settlement of dust on the bottles.  Communications were vital to deal with this situation and avoid abortive work.

Another area which created some tension was with the breaking out of the old escalators and staircases which created lots of dust.  This pushed people to breaking point and a ‘janitor’ was made available by Bovis to deal with this problem.

Achievements such as when screens came down were celebrated amongst the M&S staff as this was seen to be important in dealing with the disruption and developing the sense of milestones which were being met.

Communications

During construction weekly team meetings took place as well as monthly focus team meetings.  The weekly meetings were concerned with the immediate short term, the next phase, the bigger phase and floor by floor issues.

An informal newsletter was also produced by Sally which aimed to make people aware of construction activities (see Appendix 1).

Post-Construction

As the construction works were completed on a phased basis this provided an opportunity for two opening ceremonies and two shots at publicity.  Celebrating achievements was a key aspect in rewarding and motivatinfg staff, an example being a bucks fizz breakfast with top rated Michelin chef Paul Heathcote present at the opening of the food hall.  The major of Bolton also performed the cutting of the ribbon.  Nat Lofthouse opened the main store.

After construction is complete there is still the task of making the extended and refurbished store work, which is another learning curve the store team need to negotiate.

4.0	Project Review

A problem the store experienced was the feeling of being in the middle of a complex relationship between Baker Street and the Contractor, ‘piggy in the middle’ if you like where communication problems between these parties made life very difficult in the store.

Critical Issues

In the redevelopment of an existing store what is important is maintaining the quality ‘environment’ which is provided for the customers.  The aim is to avoid extremes in the ambience within the store, critical areas of concern being hygiene, lighting and heating.  Specifically, areas of concern which tend to occur at the interfaces of construction and retail are:-

- hoardings screening construction work require to be clean and to a high standard.

- dust which is produced during construction can create a hygiene problem and merchandise must be protected.  At Bolton double layers of polythene were used as protection.

- lighting must be provided where screening affect the balance of natural and artifical lighting within the store.  At Bolton neon strip lights wereutilised down the sides of the hoardings.

- Re-development invariably has a large impact upon a stores takings during construction works.  The role of the store team is to minimise this disruption and losses and ensure quality and a smooth operation is maintained.  The redevelopment of M&S Bolton resulted in estimated sales losses of £1.5 million.

- Must develop the ability for all parties to learn from the experience.  Recently 6 stores have been completed and if lessons can be learnt this will help contractors and the M&S Team (store and HQ) and will ultimately benefit the customer.  The knowlegde which exists with people who have experienced redevelopment needs to be captured so that lessons can be learnt.

- Lessons Learnt

- ‘inform staff- involve staff- celebrate with staff’ to ensure high levels of customer satisfaction are maintained.

- IT contract for any future store should come under Bovis team responsibitities.  This provided frustration for both Bovis and M&S.

- Timing of construction activities important to avoid key retail times.

‘The way particular events are dealt with, whilst not threatening the relationship produce friction and emphasises the difference in culture between client and contractor organisations and the need for effective communication’.

Suggestions for Improvement

‘Development Pack’ needed providing details of contact points, equipment requirements and details of recurring problems to be aware of.

Computer walk through of finished store would help with appreciating sight lines on each sales floor with repect to columns , tills and wardrobes.  This would help to sign off a lot of queries early on.

5.0	General Comments

Retail is a dynamic industry and on any project there are many unknowns (affect of bomb upon programme and opening dates, for example), and when stores are being re-developed teams must be prepared to change and flexibility is essential.  This creates a lot of stress for all involved and the task of managing this is complex and requires sensitivity.

Further, M&S are what can be termed a ‘professional’ client due to the amount of work they undertake and expect high levels of health , safety and hygiene to fit their corporate image.  This provides a particular challenge for the construction industry.

Benefits which could arise from developing learning nets of store liaison staff who have experienced development projects.