Adversaries or Partners?  IMI EPSRC Research Programme

University of Salford

Interview ‘Summary’ Report

Date:  		20th February 1996

Interviewee:    Keith Bingham, Project Manger, Northern Foods, London Colney

Location:  	Trafford Park Bakery

Interviewer: 	Stephen Allen

CONTENTS

- Personal Background

- Project Summary

- Project Story

- Pre-Construction Phase

- Construction Phase

- Post-Construction Phase

- Key Factors

- Suggestions for Improvement

- Personal Background

- Keith Bingham has worked for Northern Foods for 17 years. The last 8 or 9 of these has seen him involved with Bovis in particular capacities over a range of projects, including two large jobs, Pennine Foods and London Colney. He has also worked on Northern Food’s projects with other large contractors such as McAlpines. However, the majority of his experience has been gained on smaller refurbishment projects performed on an ‘in-house’ basis with no external main contractor. In this arrangement the Project Manager adopts the role of construction manager and co-ordinator in a ‘Construction Management’ style of procurement. This style of procurement and project management has been reasonably successful on these projects but brings it’s own burden of responsibility and risk not faced in larger jobs where large contractors are used.

- Project Summary

- The project was successful and in some ways there was a good ‘construction’ team, though a few problems surfaced during the project duration. (But, a question remains as to whether the partnership was successful). The final product, a road distribution centre (RDC), was delivered roughly when it should have been, roughly to the cost which was expected and roughly to the anticipated quality. With regards to the programme, all key dates were met (except one which was missed by agreement). However it was felt that overall the job was dissapointing in a number of aspects and could have been improved upon. This dissapointment may have been due to peoples original high expectations which were increased through ‘hype’ surrounding ‘Bovis effectiveness’. Whatever the reason, it seemed that this feeling was mutual and ran throughout the site team. The major frustation / dissapointment for Northern Foods was the feeling that they had been let down with respect to quality, in particular with the standard of finishes in the facilities offices.

- KB had a number of personal grievances / annoyances on this project:-

- A problem with the effectiveness / cost-saving initiative was that the scope was increased through increased expectations but the budget was not. When Bovis said we’ll build you this project for £6.5 million rather than £7.5 million NF’s reponded by saying, ‘people expect us to spend £7.5 million, we’ll build more, this is an opportunity to create space’. So the project was amended to spend £7.5 million but it was felt that Bovis would have prefered to spend £6.5 million and for NF’s to go elsewhere with the £1 million contract. (Also at some point there were discussions as to how best the £1m could be split in the form of a profit share between Bovis, NF’s, and the architects. KB felt this split may have been unfair and the structural engineers, electrical sub-contractors and other key sub-contractors may have been involved. KB clearly felt that this was a saving to the client and he should be the sole beneficiary. However, it was recommended to speak to David Short, now with Cleggs Construction, for more information on this split.

- Quality Management / Assurance System which Bovis were operating on this site was claimed to be second to none but KB felt that on this job it operated merely as a paperwork exercise. Site-visits were undertaken by Bovis QMS people who came and audited the project but no results were available for weeks. This failed to identify production and quality problems on site and the feeling was that NF’s and the architect were let down.

- The feeling was that a number of sub-contractors did not produce the required quality and hence some packages did not provide the required ‘value-for-money’.

- Who was the Client?

- Another problem which was raised was the fact that the project team did not know what was being built (concept - yes, detail - no) even as works were progressing. Everyone knew that it was a warehouse but what was going inside? This was put down to the clients need for flexibility and their dependance upon market forces (client - Sainsbury’s, NFT building occupier, NF’s building landlord). What was to be held in the warehouse determined the interior layout of the facility (paper or tins?, ambient or cold-chill?, mobile or static?). This interior layout would obviously effect various construction details (i.e. aisle width, narrow or wide, has a direct influenece upon where light fittings, the sprinkler system and CCTV are installed, and also positioning of fire exits).

- On paper this was the ‘easiest job which had been undertaken between NF’s and Bovis’, however the reality was that for a variety of reasons problems were encountered which proved to be far greater than were anticipated. The site proved more difficult than expected and this may in some way be due to the involvement of NF’s, NFT, and Sainsburys. The lack of information at certain stages led to problems but it was difficult to go to Sainsburys and make demands in case they went elsewhere. (organisations within the industry afraid of upsetting clients in case they go elsewhere, an unnecessary risk in a difficult economic climate SA)

- ‘It would have been a great help to know what was being built at the 	beginning of the project...’

- Conflicts

- It was stated that a general conflict of interests existed between the parties; Bovis are a commercial organisation, a construction company who are in business for turnover and profit which thay may do more successfully through ‘partnership’ and ‘effectiveness initiatives’; on the other hand when NF’s procure a building they want as much building as possible to the highest standard at the lowest possible price. Naturally this situation creates potential conflict situations which need to be managed.

- The effectiveness initiative (E.I.) document (Appendix 1) did not tell the full story. Written after the event, statements are included in this document which make the whole project sound like it was more successful than it actually was. It was true that cost-savings were made on the project but the feeling was that NF’s bought less than they thought as a result of omissions and reductions and lowering in specification.

- Pre-Construction Phase

- It was stated that a nice ‘cosy’ relationship existed between Haydn Worthing and David Brearly which was beneficial for the ‘partnering’ arrangements overall. (During construction Haydn was on site roughly once a week, David once a month).

- NF’s purchased the site from a developer who went bust and became responsible for site buildings, site roads and a pond. This estate management role was not an ideal situation for NF’s who would not want the responsibility in the future, they would prefer someone else to own it and to rent it from them. Their intentions are to sell the facility on to a pension-fund in the future. Because of this ‘Institutional Design Standards were required providing a commercially acceptable standard with reasonable offices, adequate car-parking and landscaping. The purpose of this is to make the facility more marketable.

- KB started on the job just prior to the start of construction with the design team and Bovis appointed and in place. This was considered to be rather late for KB to become involved with the biggest part of design had been done though as building progressed changes occurred through necessity. At this point in time KB’s experience indicated that SBT Architects were more infront with design work than is usually the case in most projects.

- Just before construction started, Colin Andrews came to teach the ‘team’ about Bovis effectiveness’. However KB felt that this occurred too late to implement the initiative successfully, which was based around three key aspects:-

- cost savings

- procurement

- team-working

- The concept presented by Colin Andrews was that all professionals and sub-contractors were competent and the idea was that they self-certify their work with the goal of zero-defects. This effectiveness initiative was the crucial factor which made this project different. The project was centred around ‘Bovis effectiveness’ rather than ‘partnering’. At the start of the project KB’s feeling was that he suspected the whole thing would not work but it was difficult to isolate reasons for this feeling.

- The Bovis / NF’s relationship had never worked with SBT before, but their upfront work was very good with excellent drawings and specifications. However due to the E.I. all this good work was ‘pulled apart’ due to enforced changes creating many frustrations and also generated the feeling that the ‘brief’ had not been right. This resulted in obvious problems in team ‘co-hesiveness’.

- ‘...from the outset of the construction process there was conflict between (a), 	the developed brief, (b), institutional design standards, (c), ‘fitness-for-	purpose (whose or what purpose?), (d), the Bovis effectiveness initiative. This 	created contradictions, constraints and increased complexity which ran 	throughout the project and resulted in extra tension within the the 	relationship...’

- Also due to the involvement of Bovis Cost Consultancy there was a feeling on KB’s part that there was no independant QS which he felt created a strange relationship. Obviously great trust was required in this arrangement but was this trust present?

- Construction Phase

- KB was on-site for 3-4 days / week and he shared a hotel with other ‘team’ members. This provided an opportunity for people to ‘gell’ if they got involved in the various activities which were taking place. This helped to establish and develop teamworking.

- Tendering also presented various problems and was carried out on a rolling programme as construction works progressed. NF’s was not involved with the choice of sub-contractors except for nominated specialists (e.g....?). Other sub-contractors chosen to tender were selected by Bovis who were employed to manage construction activities. Through the tendering process saving were made from the agreed budget, as required by the E.I. but KB felt that they didn’t always buy better, in fact in some cases they bought less. He felt there was problems with value-for-money but he acknowledged that this is a diffiult situation:-

- ‘should you always go for the lowest price?’

- There was a feeling that the lowest cost packages were chosen using the cheapest materials with the result that some contractors were chosen who were not up to the job in terms of cost, time, quality and this resulted in very poor workmanship in some instances. Particular problems were experienced with:-

- Concrete Man

- General Builder

- Joiners

In light of the problems experienced key factors ro concentrate upon are contractor selection and programming works.

Fast-Track Construction

The project was a fast-track project, working to strict deadlines for a demanding client. Problems were encountered through trying to work to a tight schedule yet also trying to buy things cheaper and to make cost savings. Fundamental problems were experienced when minor defects were not corrected as and when they occurred. These need to be corrected as you go along, either hourly, daily, weekly it doesn’t matter as long as you don’t allow things to build up. KB was unhappy with the attitude of ‘leave it until later’, as people get used to lower standards, the work is accepted and in the worse case scenario mopre work is carried out over the top of defective work which then needs to be done itself and creates the problem of, who pays? (e.g. defective plaster on wall, -painted, -room carpeted, all to original programme and then the plaster is removed. This creates bad feeling, frustration and arguments over payment).

So, when attempting such an ambitious method of working combining the fast track construction of a building which is not fully specified, effective communications and accurate information are essential. Unfortunately when work started there where various packages where information was not being passed on and changes were being made which impacted upon other contractors.

An example of this was a breeze-block wall inside the RDC which was to be plastered. It was decided to just ‘fare-face’ point the wall and the cost of plastering was taken out of the budget. However for some reason after the wall was half built the colour of the blocks was changed with a resulting unseemly mess. There was no money to plaster over this, and in the end the wall was painted four times.

This was referred to as effectiveness gone crazy, where the final solution takes more time and costs more money than the original idea and has a negative effect upon the relationship. There was a feeling that the specification was changed without fully evaluating the effects of these changes. Another rather flippant example but which makes the point well was of blue carpet in the original brief being changed to another colour which clashed with other fittings and internal decoration. The ‘essence’ of the E.I. was right in some ways but it needed to be reported back to the design team in time so any changes could be evaluated holistically in terms of the whole project. Savings can be a good thing. ‘Communications were not as good as they needed to be in order to play this game’.

Problem Areas

90% of the job went relatively well but the last 5-10%, the crucial bits which everybody sees created a number of problems. The structure was generally OK, steelwork, concrete an brickwork. There was a problem with the ‘external’ concrete contractor in that the ‘yard’ turned out very complex. Despite this this progressed quite smoothly in spite of client requirements for existing yard to remain operational and for a phased handover of the extended yard (100 lorries / hour continued using the existing facilities at London Colney during construction). Defective slabs are still being repaired now but as the whole facility is operational it is difficult to say which is a result of poor construction and which is wear-and-tear.

With respect to finishes, the buyer thought he wasn’t getting what he was paying for, value-for-money was being questioned. He did not think he was getting good finishes, not what he had asked for and not what he wanted.

Safety

A very positive aspect of the project was the safety record. Within the project emphasis was placed upon safety and London Colney was a very safe site with only a few minor accidents. The project won the Bovis Safe Site award, 1994.

Post-Construction Phase

The project was ‘completed’ and handed over but two years later some problems are still being argued about. KB stated that he had a briefcase full of defects, the first snagging list ran to 22 pages of defects. He also stated that he sensed the Bovis attitude was we’ve done you a ‘cost-effective’ (i.e. cheap) job, what do you expect? The biggest aggravation came at the end of the job with the snagging when the building had been occupied.

Problems are still being experienced 2 years after ‘completion’ which were attributed to the E.I. One particular problem is the ‘playing fields’ which were planning gain for the parish of London Colney. Through the layering of top-soil over clay from the site strip grass won’t grow and a footpath floods, ‘an absolute mess’. Now things are getting nasty and St. Albans District Council is threatening to take NF’s (?) to court. Bovis claim no responsibility for this problem but an argument persists between Bovis / NF’s / the landscape sub-contractor / the District Council. Meetings are still taking place to resolve the issue.

Key Factors

Teamworking

Effective communications between ‘multiple’ stakeholders is an area for concern

Suggestions for Improvement

Rectify defects as and when they occur, rather than allowing them to accumulate which results in lots of abortive work and causes frustration for all concerned

‘Time against us’. Should have more time to evaluate costs and settle the design. This was carried out during the construction phase but a tight programme, extended works and a changing brief created difficulties in keeping control of both the finances and production sides of the project.

Freeze design earlier, possibly involve contractor at an earlier stage though this is difficult in reality due to the nature of the business.

Have clearer guidance from the client what is being built.

Clarification of ‘fitness-for-purpose’ at early stage and relate this to ‘institutional standards’.