Interview Notes

Monday 1 to be included

# Monday 2

Christina Gold

# BAA

Design Team Leader

Pavement Team 9 Months

BAA 7 Years

Initial workshop was attended and there was a follow up workshop. There have been no team building activities regarding the partnering and the partnering workshop was not followed up by senior management.

There should have been more people at the workshop

There still needs to be more integration of design and production team. Things have improved in that they know who to talk to, They come to us now, however they still wait until the design has gone to site before realising points.

Problems with specification still exist and their is still unnecessary delay due to changes occurring.

Construction started but the design is still going on. Drawings can still be late and often are due to time constraints. (considerable due to continuity problems and BA requirements changing at short notice.

Concern was expressed over  working exclusively to partnering. What if the relationship goes wrong?

The need to preserve traditional ways of working was seen as unnecessary especially as BAA have other project not in the Frame work.

General improvement areas are targeted but specific job related ones are not.

Partnering hasn’t made her job any easier.

Feels that companies are growing but individuals are not

There is little relationship between the design team and supply chain.

Believes the policy should include greater incentives for staff.

The partnering needs developing a lot more.

Everyone wants the partnering to work however.

It is encouraging that new tools are to be introduced such as a new change process where ideas are put forward, it is then assessed by an evaluation team (relevant personnel & client) and necessary research and is then implemented or dismissed.

Project process is high level and there is no  design process. Roles need to be defined more.

Responsibilities need to be set out as well as how people relate to each other.

## Benefiting the company but what about us?

There is little effective IT integration in place and there  is no standard system for intranet development either on site or between airports.

### Benefits

- Enjoys the additional responsibility

- Easier tendering

Removal of site supervisors and introduction of self assessment has simplified site management and reduced adversarialism. The site engineers are generally AMEC.

Monday (3)

Steve Marsh

Amec

## Commercial Manager

6 Years

Job: Saw an opportunity for promotion.

Pre contract cost planning and the collection and feedback of cost information & cost reporting

##### Job spread

2 Gatwick

2 Stanstead

3  Heathrow

No real introduction to partnering and the first real taste reading the tender documents.

Teams recognisable however works mainly with individuals and not teams.

I prefer to work with any one who’s in with the partnering schemes.

Originally there was no formal assessment criteria although financial health checks are carried out. Now after two years there are some procedures in place. The first main question asked is how much cheaper was this than last?.

The CIP is something that really needs sorting out. It is not just a part of the partnering frame work ad there are other areas that need sorting out.

Identification of a measurement scale for bench marking needs to be developed.

Believes AMECS risk is negligible

BAA’s risks are reduced slightly

More responsibility for everyone on the pavement team however there are few other benefits.

A reward scheme might be possible, however How does it fit in with AMECS other work.

Partnering at present doesn’t allow payment incentives.

Different parts of company’s partnering. How does this fit in with existing company policy.

Amec procedures aren’t written around around partnering. Either rewrite or adapt one or the other.

E.G. BAA and AMEC have different month ends for doing the accounts

A chairman (partnering champion) needs to be appointed always. The partnering needs to be managed. it won’t happen on its own. Existing management can be used but must be aware of what the partnering requires.

## Benefits

Far more openness than traditionally.

The formats are in place for assessment. hmmm

Dealings with subcontractors more open and more involvement.

Dealings with sub-contractors have improved and there is far more openness than traditionally.

Frame Work Agreements with:

- Redlands

- ESM sealing

- Concrete Cutters

- AB Stewards Electrical

- Earths PJ Brown

- Tarmac

#### Policy document

The responsibilities of organisations and individuals must be sorted out. These are not resolved at present.

How to be people relate to each other?

What is the policy document to be sued for. Marketing or operating the partnership/s/?

Monday (4)

Andy Delcher

AMEC

# Planning Manager

With Amec 14 years.

2 years

Received as much information as anyone. Generally a clear definition i.e. working together to be more effective.

The first workshop was however to late. After the selection of AMEC management were keen to get the framework up and running and there was no clear structure. We went straight into a ‘pile of work’. A second workshop was held 3-4 months in.

Amec and BAA have different type of management structure. BAA have a relatively flat structure  and Amec a hierarchical one. They have different ways of doing things and integration can be problematical. Furthermore the functional aspects of the partnership are reliant on three organisations, being AMEC, BAA and Gatwick Airport Ltd Within Gatwick  there are three further sub set organisations groups consisting of operations, maintenance, and security. Integration with these three can also cause problems.

In the last year GTS (Gatwick technical services ) has become more integrated.

There are problems with  any sort of group. We had to take people out of the team who wouldn’t fit. They have done this.

The workshop instructed us to give the new team a common identity hence the ‘Pavement Team’.

Little team building has not really occurred regarding BAA , Amec however it is v important to initiate team building activities when partnering short term.

One problem is that there is quite a high turn around of staff on one of projects. We would like to improve continuity but it is very difficult. You are continually at the whim of the airline. Work dying off is a real problem. At first there was no real security and staff had to be relocated. Now this is much better due to client representative and the senior level representatives. Now there is a single communication point. All report to George then talk to John Moss.

Started off with documents now developing with the team.

There are problems with the softer issues such as the political aspects.

Environmental, publicity, people issues.

Regarding problem solving techniques this is not a problem. Engineers are problems solvers, and it is a question of allowing them to do their job effectively.

Moving away from Parent company procedures is not a problem. Incentives are needed from the parent company.

40 % of the programme can be saved due to partnering.

E.g. Tower stands

Feb/March 2 weeks

4 stands

build all eight.

Money released in tranches.

The partnership is about dispute avoidance and not simply resolution. Most disputes come down to money and the way you pay people has much to do with the number of disputes that arise.

##### Payment

Started off with gain share. Amec receiving 50% of any savings above and over the target cost. The result of this is that Amec want it early and BAA want it late. Gain share didn’t work.

It is better to set target cost when suitable. A percentage of the target cost is then allocated to Amec as its fee and ring fenced. If you bring in  under you gain and so does the client. Precedent and the understanding of the particular job type makes this process easier.

The client is therefore taking back a whole lot more risk.

Supplier selection has changed.

##### Personnel

Has to do with the way in which you incentivise people.

##### IT

Amec are not IT literate. They are learning a good deal form Amec.

Policy Requirements.

Budget is vital

Being prepared to adapt Amec to client and project.(Most of the problems arise with AMEC the parent company and not BAA Diagram of new organisation splitting off from Amec parent company)

What do Amec want from the policy document.

Tell AMEC to address client requirements.

Monday  (5)

###### Geoff Lang BAA

Site Adviser/ supervisor

Designer, Engineer

In a good position to assess level of design integration.

One of the original pavement team. A site advisor.

Has been with BAA for 25 years. I was not invited to the partnering workshop nor the follow up.

Originally the partnering was poorly managed. Know one knew which way it was to go. The 30% saving was the driving force and what everybody was familiar with.

The design has been sharpened up since the partnering. Cannot accept failures and are trying to reduce over design and consequent wastage. However safety factor is still required. Critical on such work.

Integration between design team has been improved with constructors sitting in on meetings.

Standardisation of drawings is being undertaken at present. Next month we hope to standardise 95% of drawings. Standardisation is a necessity on such work due to the repetitive nature of the work. Need to work with the package contractors. (3-4).

There are 6 people on the design team and occasionally an agency draftsman is brought in.

CIP

Previously the push was in total quality. BAA have always had a policy of looking at new products. Now with the AMEC partnership they have more information.

The Generic stand is used for measuring the success of particular projects., benchmarking costs in particular.

E.g. Concrete

Service road

Floodlights

Fuel rigs

Taxi way link

Pre framework £1.2 million post framework 0.9 million.

Cut back to design. Now more cost savings to come form sharpening up the process.

There are meetings and brainstorming sessions although sub contractors very considerably in accessibility.

Gatwick airport have accepted greater risk through the partnering. Previously they had there own supervision on site for example:

- Resident engineer

- Assistant engineer

- Clerk of works

- Inspector of works

These have all gone now. There is now a quality control manager (BAA) who has replaced the clerk of works. He looks at quality but there is not the rigorous monitoring that used to happen with the above. TRUST is the key which enable the Work package boys to get on with work. It is presumed that teams are capable and continual checking is not required. However Geoff feels that in some circumstance there is not enough site supervision for example with the Asphalt boys. (Contractually not bound).

Familiarity is the key and as the jobs have progressed people have got to know each other. This makes it undesirable to have to replace teams and there is a conscious effort to reduce staff turn over. Staff are moved around between airports if there is a lack of continuity on a particular site. Furthermore the pavement team try to go back to the same companies.

## Benefits

It is good to have Amec in the design offices (at Jubilee House) regarding:

- Accessibility

- Familiarity (working with the same group of people

In Geoff’s view no one loses out by Partnering although there is a possibility that the client might potentially lose out due to the lack of a clerk of works if things go wrong.

## Improvements

A sharpening up of site processes is required. They used to write operational procedures about how to build something on site. They should change the design process to suit these procedures.

BAA want the client to give more time to do design.

A design freeze is required to reduce last minute design changes by operations or changes in the brief.

Communications need to be improved drastically and if anything Geoff feels things have got worse in some instances. Communication works well at top level however the site worker level things are bad with operatives simply not being briefed effectively enough. Previously meetings were held at the end of each day regarding the next days work. These pr-briefing sessions were invaluable in avoiding numerous problems that might arise due to unfamiliarity of new operatives to the complexities of the airports. These were useful in improving the level of awareness of site workers. Normally the site foremen would give the briefing. Now the approach is trusting them to do the work effectively first time. Trust is important but so are such briefing sessions.

# Monday 6

# Nic Yeoman

###### Amec

### Production Manager

There has been little training for people at senior level.

There was the workshop which took place three months prior to the site work starting. This should be done with the sub-contractors.

BAA were very short term previously.

Initially teams were not very well defined.. Communication needs improving .

Teams are to take collective responsibility although individuals need to be identified. A no blame culture is being fostered. There a strong push to ’empower the front line’ This is not formalised at present.

There exists an issue resolution ladder which is projects specific and partnering specific.

There isn't  present one proper sub-contract framework  agreement in place with Redland.

Pain share/gain share. Fixed fee for sub-contractors as with Amec / Gatwick/

What’s the difference between one job with £10 M of pipework and 10 jobs with £1 Mill.

There is a great effort to introduce CIP initiatives and process mapping. There are observers out on site mapping procedures. This can be done due to the repetitive nature of the job. There is a need for more efficient data collection systems.

Benchmarking is required. Not necessarily with ourselves but with other companies.

There is not enough investment in training at present. Some times teams miss the objectives.

The pavement team is capable and there is opportunity for younger staff. Personality is important. Some were good at their jobs but would have destroyed the framework.

BAA is a large operator with 40 contractors and 120 suppliers. Many different disciplines are employed by them and they have other frameworks in place such as structural, civil and tunnelling frameworks.  There are 7 supply groups (the pavement team are supply group 6)

Originally the procurement policy was all pain share gain share. A target cost was prepared and  participants would share in success. Base don actual cost(small 2.5% profit) .

Despite the incentives the process ran into problems as there were still changes required and much time was spent discussing whether something was a compensation event .Now there is ring fencing.

£450 million/year and £1.4 million capital infrastructure.

You need a lot of trust for projects this size. BAA expect Amec to pay for the resource. (Investing)

What do the staff get out of partnering?

- More responsibility

- More autonomy

- Opportunity to show capability

Policy Document

Should illustrate partnering strategy

BAA set targets

Cost reduction predictability

Time certainty = predictability

Safety

Amec must get involved.

The policy document must show that Amec has got to change. Many of the parent company documents are written with the traditional industry in mind and focus on the avoidance eof liability by Amec which can be against the partnering grain.

However trust based relationships are not always the best solution. Due to the diverse nature of Amec work (even civils due to country, etc) partnering will require heavy modification in some instances. The policy document should take this into account.

Also document should stress the importance of finding the right people with some tools and techniques.

Training must be emphasised with a form of training programme.

Should occur through out the company. (internal partnering philosophy)

# Tuesday 1

# Steve Sage

Amec

Site Agent

3 years as agent, 8 with company.

2 Jobs running at present

Went to workshop and had individual chats with managers.

There was a follow up day to the original workshop after about 1 year. Steve was one of the first people on the partnership and the project kicked off the same as usual. The partnering philosophy or idea was spread by word of mouth.

Work in clearly defined team( always with team) mainly AMEC.

Initially had BAA members in team but some did not work well with the team.

The site staff on the project are closely knit and the site team is mainly AMEC. There is a clerk of works who is BAA.

Clerk of works reduced through the partnering policy. There are now 2 resident engineers.

The design team integration is better since the partnering and the designers and production disciplines are attempting to get involved at the front end. ‘Production tam and individuals within have always tried to build as effectively as possible’

- Partnering has been a benefit. Contractors have always had the intention to work closely with other disciplines. Cannot operate in isolation. Effort has been spent in building up relationships. Now they have direct access to Maintenance

- Operations

- And security

Before they would not have had access to such departments.

With partnering they know they have to achieve 30% cost savings but are not sure how to achieve this.

‘For improvement we need access to others’ such as head of security and Nat’s (guidance system personnel).

In the pursuit of continuity and keeping staff directly employed personnel move from airport to airport.

There are different personnel at the various airports and their exists a considerably different attitude. BAA teams are different at each airport. More of Amec staff move about.

The partnering concept is easy. Implementing it is more difficult. There must be senior staff commitment to change. Site teams do not get enough support. BAA are supposed to be partnering, AMEC are, but what about Gatwick Airport ltd?. For effective partnering they must be as involved and committed as the others.

Other complications in that BAA run the airport. If they want something everybody jumps. There is might change regarding flight paths and numbers.

Trust in the team has improved dramatically. Teams are left to get on with the job without persistent monitoring. Individuals have greater responsibility and they can now get their point of view across more easily.

Partnering is not filtering down to site teams from senior management.

Operational part of the airport should have been included in the workshops.

The first 6 months of the of the agreement was run as a conventional contract. The clerk of works was being disruptive, hence the removal of such personnel.  It is critical that people gel. For those who have committed to it there is a sense of achievement, greater enjoyment and greater support form the framework.

Policy Document

Lines of communication need to be understood (for your own company and with partners).

The parent company issue is not seen as a problem.

Policy should include responsibility guide. (or a procedure).

Tuesday 2

Paul Clarke

AMEC

Arrived on present job in November 1995

Stints with Amec of 2.5 years and 8 years.

This is his first experience of partnering.

#At the workshop there a lot of negative people. There was a follow up in May of 1997. This was selective and there was considerably less people than original AMEC, BAA staff.

The partnering seemed unfocused at first. However it is definitely a more positive way of working.

The team at Gatwick is good. However the teams at Heathrow don’t seem to have gelled as well as at Gatwick.

After the big workshop some big changes occurred but these were due to financial auditing not partnering. The financial auditing  by a big company was a help. BAA have a different arrangement. (Dealing with VAT invoices trying to cut down number of invoices.

Partnering benefits : supplier integration is much closer.

Supplier framework agreements.

Clear invoices before , better admin.

Currently there are several trial framework agreements on trial consisting of :

Greenhams

Tarmac

Topmix

PJ Burns

Gatwick airports Ltd. is still difficult to communicate with. For example passes. AMEC have to pay up front and then invoice Gatwick. Is this in the spirit of Partnering. Policy document should address this.

Originally people became complacent. Controlling and monitoring mechanisms were there and are good but they were not being used. There were £1million pounds worth of involve queries as a result).

Previously there was a lot of survey wok. His has now gone. We must get it right at the beginning and not argue about it at the end. Furthermore there is a requirement to be very careful regarding material selection.

There have been major task changes  for many. All require better information about the importance of monitoring. Partnering is saving money. There are new initiatives in the pipeline. The invoice queries have gone down from £1million to £0.25 million.

Personal notes

I have the team available to do the job.

I am able to be a lot more proactive

Company culture must change as problems are caused by people outside the site teams such as senior management and particularly the accounts department can cause problems.

Must: use QA procedures, get the best people for the job and avoid complacency. Also partnering can become boring and repetitive if there are no new ideas.

Policy should include or reflect ‘new method’ systems and should included ’suggestion box system’. Old systems do not have to be completely thrown out and the good points should be included with partnering.

Tuesday 3

Geoff Packer

AMEC

Labour Administrator

Is involved with all three sites and deals with labour only suppliers.

Not at workshop and the partnering approach was only communicated to him at meetings. Partnering he believes does not really affect him.

The current procedures work and main role is to check allocation sheets and the paying of wages.

11 Gatwick

29 Heathrow

!! Stanstead constitutes  weeks work.

If things go wrong he knows who to talk to i.e. Foremen.

From an observers point of view the pass system seems problematic.

Not in contact with partnering scheme but aware of it.

Tuesday 4

Dia Redman

AMEC

General Foreman

3years as Foreman, 23 years with company. Was at the workshop and found it very informative, although AMEC has not produced a strategy or information subsequently.

Personal relationships are generally good although there is some BAA/AMEC conflict Some initially were not compatible for partnering. The removal of the clerk of works was not an unpopular move as he did not fit culturally.

The senior staff are accessible.

Design team integration is improved.

Job

The job is now much easier as you are not looking over your shoulder. You are left alone to work. Furthermore design integration is much better. There are still problems such as lack of drawings and late drawings although this more to do with BAA and Gatwick airports than the design team.

There is no integrated change control system, ad the improvement programme needs greater sophistication. There are also restrictions imposed due to the continual pursuit of 30% cost saving.  This results in money being saved on labour!!! With the consequence that quality is adversely affected. For example 200men were tried out in 12 months. They were trained and then let go. (6-800 staff turn over in 2-3 years and these people need passes at £30.00 a go. This is not cost effective. Furthermore there is no real selection criteria. The subcontractor is told that more labour is required and some are sent over There is no investigation into history or capability. Many young staff are brought in. Experienced staff won’t come due to poor rates and hours. This has not really changed since the partnering (is no worse but is certainly no better) and requires attention. Partnering should tap into experienced workers. Perhaps subcontractor to full time for labour provision.  However there is a push to go form LOSC to directly employed.

Discussions have been made with Browns to bring n more experienced staff.

Things don’t seem to be as bad at the other airports.

There is also to much paper work.

Policy Document

A strategy to let people know what is going on is required. People need to know what they are supposed to be doing and why. Incentives.

‘Ever one needs to know how they fit into the process and what is expected of them by the partnering agreement.’

Tuesday 5

Alison Ramsdale

AMEC

Planning Engineer

6/10 years in the company.

Role: project planner and deals with agent (Steve)Must make sure it can happen when it should. Chasing of information and co-ordinating when it arrives. Didn’t go to the workshop (any of them) although some strategy was explained. Doing a business IT course.

Work since the initiation of partnering is more pro-active and has gone up in responsibility.

Far more integrated with designers and c an go into the process with eyes more open. Good levels of personal integration with BAA design team.

Also proactive with suppliers.

All airports use some frame work suppliers (40)

Suppliers are used between all three airports. AMEC get some clout with suppliers because they all want to get into the framework. They aren’t perceived as a contractor.

Meetings with subcontractors are held every week and all know of the partnering scheme.

Some people in BAA are obstructive for example security with who  have to be very careful.

You need some one with some clout at the BAA meetings. Sometimes difficult impressing changes on people. People hate change. Better relationships with Engineering Duty Managers and Operations.

With the pavement team success has been made in that there is a seamless integration of BAA and AMEC staff.

Use of both names (BAA and AMEC) can help in certain situations.

The continuous improvement is far more organised. Improvements in efficiency for example with one pit Gang going between both contractors and airports.

Initiatives look at :

- Wastage

- Pavement quality

- Wagons timed

Such monitoring was undertaken before the partnering. Risk on concrete due to whether. Efforts made to minimise problems. There are also end of contract reviews with each of the sub contractors .The CIP aims to reduce risk as far as possible.

Brainstorming meetings including all people are undertaken regularly. (Everyone and anyone form different levels of management / site staff).

Long term strategy is being addressed although BAA have more people involved in the strategy.

- IT

- Email on site

- Drawings on paper

- Weekly information on drawing updates.

BAA are not that IT literate or sophisticated. There is no proper integrated IT system. BAA and AMEC have a completely different set-up on different platforms.

Alison would not be able to go back to the old system.

Would like greater sharing in success and more incentives to overcome repetitiveness of tasks. The bonus received (Amec) is not based on the partnership. (Consider in policy document)

Long term strategy needs to be concentrated upon

Duncan Ovrey

Site Engineer

Earth Works Drainage

AMEC

4months in team, 3years with the company.

Out on site 90% of the time.

Didn’t go to the workshops

Was given a brief resume of partnering. Had no other information. Can see the continuity of work with partnering.

Tower stands, 4 months then briefing and resume. There is an overview of goals and management structure.

Even in four months you can see the continuity. There has been a significant smoothing of the edges.

Trust is vital and requires strong QA.

There is still a perception of them and us however. Work is going on but thing s could be better. BAA are still pulling the strings. BAA don’t have enough give and take. We are cracking on as best we can and in theory the agreement will sort out things. I never see the design team however the practicalities of getting them out on site is difficult.

The standardisation that is happening at present is a big help and its definitely the way to go.

Traffic management is often discussed between BAA and Amec illustrating the team work which is going on. Landside/airside  limitations and restrictions make getting about extremely difficult.

The lack of a clerk of work involves quire rigorous QA procedures and documentation. More onus due to the lack of the clerk. BAA trust AMEC to do the work effectively and don’t employ the clerk any more.

Head of BAA used to run Jaguar and is experienced in the AM industry. His driving force is to reduce costs by 30%.

How much should each party give when partnering however. Is it equal or is it that we are still employed and should do what we are told. The benefits of partnering are not self evident to those persons on site.

Losses and profits being shared is a good idea however this is not well documented. More of the sharing of risks and rewards needs to be explained.

There is a feeling by many of the sub-contractors who have worked for the airports for a long while that AMEC have pushed them aside.

Mark Lloyds

Section Engineer

Tower Stands, services and structures.

Working for Amec for three years( previously 18months on north circular).

Based at Gatwick although has been to Heathrow for 2 months. They still have a clerk of works there where as self governing at Gatwick.

Received no training or documentation besides the basic organograms.

They are partnering with BAA engineering and not BAA as a whole. There is therefore problems with integration e.g. security. Initially there was man marking from BAA and there was added pressure as a result. Furthermore the separate salaries and conditions of BAA staff lead AMC personal to question whether they are losing out or not. (overtime rates).

There is a feeling by some that AMEC take on more responsibility  and receive nothing for this while BAA experience savings.

Problems with other departments at the airport which can seriously effect the design and construction process. The NATS for example have been known to refuse permission for work to be undertaken and demanding changes. This has not occurred until the operatives are out on site and ready to carry out the work. There is consequently a flaw in the design process and the required personnel and department ire be excluded. Other problems have occurred with Airfield planning (BAA). AMEC site personnel often expected to jump by management. Management are always trying to make BAA happy when it might not be practical.

Undertaking earth works and drainage in winter conditions with matching programme starting in winter. Cost % will be lower. On traditional contract an additional claim would have been put in. BAA gaining (value for money).

Regarding design team integration. They are keen to get involved if there is a cost saving for them. Standardisation between airports would be a beneficial thing as at present specs and many procedures are airport specific. Would be easier for men on site and lead to a more effective cost and programming exercise.

Benefits

Less letter writing

A Learning Organisation

The design team listen a lot more than normal.

QA procedures are being modified to suit partnering which makes it easier for the man on the ground to understand.

Rarely short of staff(more time than on a major structure)

Partnering good for job security (5 Years) guaranteed. Can phase jobs, not requiring separate contracts.

Policy Document

Good for marketing but won’t help workers much. Perhaps more on strategy so people can identify with what it all about and what it means to them.

Additional

BAA have Tunnel Vision. Getting them to understand Amecs need is difficult. It is vital to get to know people and to have friends in the right places in order to get things done. More direct labour might help as well. (Pushed for at T5)/

Still problems with design drawing s being late due to lack of partnering by maintenance and security.

3monthly meetings for each level are required.

Gareth Bates

Senior Engineer

AMEC

4 years with Amec, 1 year using partnering. Used to be section engineer is now senior engineer after commencement of partnering.

Not at workshop and had to pick up the concept of partnering very much as he went along. Responsibilities are to ensure the job is OK, provision of information, programming activities, liasing with design office.

Integration with the design office is far more successful and the relationship more practical, with no QS’s involved, quicker progress and less red tape.

A relationship with Browns for Earth works and drainage is in the throws of being set up. Will help when asked to do something different to drawings and less red tape.

There exists a communication problem between many of the airport sections.

The airport authorities are not in Gareths opinion partnering, although things have got better with time due to improved familiarity

There is no continuity between the airports. The three airports are different and have different procedures. Stanstead is totally self sufficient, and you tend to deal with one contact. Gatwick requires the issuing of permits from access to hotwork permits associated with fire risk. Phone calls are and agreement are required every time you use. Variations between airports due to size differential.

Standstead are not aware of the partnering and Gareth doesn’t see Heathrow as truly partnering.

Personal view

Sees partnering as an excellent way of working if implemented properly.

Individuals can input into the process

Has gone up one to two levels regarding greater responsibility

Greater levels of satisfaction

Boundaries more frayed ?

Improvements

Airport authorities more aware of Amec needs

Greater continuity is very beneficial

Arrival of drawings is now more timely, however the design office is often not given the decisions earlier enough to undertake the work (not the fault of the drawing office.

Greater opportunity for standardisation and there is a gradual upgrading taking place. (Pavement team specific)

Development of a long term strategy? USE IT!

General

A greater pressure on site personnel to move people along.

Jobs have changed considerably in function roles and responsibilities

Design maybe more flexible but there are still delays. The agreement of senior people is required who must focus down on the needs o individual people.

Policy Document

Make sure everyone is in it!

Initiative such as a suggestion box

Development of a culture that nurtures the development of new ideas and rewards successful ones.

Specific solutions should be in the policy document regarding solutions for :

- BAA staff not being aware of partnering and the ‘joint’ team, they still regard Amec as Amec

- Increased pressure on site personnel e.g. for continuous work

Wednesday 1

Mr Griggs

Engineering Quality Manager

AMEC

Has been with Amec for 11 years and is the regional Quality Manager with the responsibility for the implementation of current management systems.

Has been introduced to partnering systems and thinks its positive but has not used a partnering system.

Differences and confrontation in the industry getting worse, with differences and commercial pressures increasing along with claims.

The pavement team is a standalone.

Regional 		Eng. QM		Pavement Team

Role to keep them in line

As far as pure construction work is concerned it should be in line with company systems. The tricky bit here is the management interface. Normally approval is required for QM procedures but with the pavement team it is autonomous. This is not normally a problem but it was initially.

Partnering is dependant upon the clients for example client change. Current client is not into partnering.

Initially there were workshops right across the board and the Southern region has had a series of workshops which provide the opportunity for the introduction of new people and for vies and options to be aired.

View on Partnering

Partnering is dependant on individuals (isn’t everything?)

Is all for partnering and believes the following are of great benefit:

Reduction of confrontation

Working together

General improvements

(A current contract has been very confrontational and is certainly not a win-win scenario)

Not really that involved!

Why Partner?

Commercially driven

Bid prices are being squeezed resulting in small margins.

Industry demands some sort of change

The parent company s very different to BAA/AMEC and has developed many of its procedures and policies in an adversarial climate. The main parent company will NEED TO ADAPT in order to integrate with its partnering offshoots.

There will be an equally big culture shock if people are asked to revert back to more traditional ways of working. People must be careful when recruiting. Graduates don’t know anything else but where you put them. There is a push by Amec to change relationships with Universities. More girls sought for engineering jobs

Client Led

If the client doesn’t want it then you can’t use it.

Partnering down the supply chain depends on individuals but can afford benefits.

There is currently no company strategy for partnering at present.

‘We should be partnering however’. Viewed by total out-turn costs if it involves a slightly better product. All eyes are currently on the pavement team to see how successfully the partnering is carried out.

Company strategy at present does not include partnering but we will have to start to change the culture of the company and clients. Successes from the pavement team should be reviewed and implemented else where. Training is critical.

Some of the relationships that Amec have with clients are long term such as the Highways agency. Long term relationships consist of two main stages, i.e. trying to get the relationships to work, and implementing principles once agreement has been obtained.

What do individuals get?

- Hopefully makes their jobs easier

- Less conflict

- More settled (but can be repetitive)

- Pavement team get recognition, e.g. photo’s and special vents.

- Senior management discuss partnering options

Wednesday 2

R.C. Noble

Geotechnical and Materials Manager

AMEC

Has been with the company for 11 years

Main responsibilities

- Materials engineering

- All concrete works

- Technical and practical aspects

- Asphalting

- Site investigation

- Pavement design

- Concrete plant

- Testing and proving

Has some experience of partnering on cost plus basis on oil rigs. BAA has similar types of agreement. Doesn’t believe that partnering is a totally new method. AMEC historically collaborates with other companies.

All for partnering. Partnering is the only way forward and can work on all projects. Benefits the scheme conception and design are done up front, a win win scenario can be created and claims and confrontation reduced. Even when dealing with BAA, under a traditional contract their were claims. Amec has seen successful American examples of partnering.

AMEC has gone out of its way to promote partnering, is up front about the procedure and is ahead of others.

In house training courses have been undertaken along with seminars and meetings. Training is underway for the whole company. Ongoing partnering is strongly promoted in AMEC.

Partnering is self regulating with less reporting in hard copy form. An open book policy is vital.

Projects : Port sea clean and Welsh Water Type of work more technically demanding, a lot more involved design process.

Believes that AMEC has an overall skeleton strategy but no standard policy statement.

Ideally partnering should involve subcontractors and suppliers (partnering chain) however this can be difficult with some suppliers and specialist subs who don’t like being open book. It requires a big culture change and is not going to happen quickly. Subcontractors that use the ICE form of contract more readily understand the required culture however.

Clients have to be open to partnering. GMP for example are not partnering because they do not want to share the risk. It doesn’t give the mechanism to drive price.

Pitfalls

Interpretation

Open to abuse

Complacency doesn’t exist in our organisation however.

Repetition can also be a problem on a project like the pavement teams. Personnel will often need to move as they become bored. Consequently there is an influx of new people. It is prudent to build in flexibility. Continuous improvement should include turnover in staff to combat repetitive work..

Policy Document

Partnering should not be set in stone as it builds in prejudices.

Requires a strategy statement and an overall policy in partnering including implementing and requirements. Should be client supplier and sub contractor specific.

Client regs

Scheme regs

Government depts

Everybody should be made aware of the conditions of the partnering arrangement ad the policy should be for all levels All parties must be made aware of the specifics of a partnership agreement.

Make staff aware that basket holders exist. An important part of partnering.

Mike Lunn

Engineering & Design Local Director

AMEC

11 Years Faircloughs

Main Roles: Engineering and technical aspects

- Work environment

- Small design office

- Geotechnical

- Quality management

- Marketing

- Technical interest

Front end

Alternative designs

Hasn’t been directly involved in a partnering team but involved in the periphery’s such as technical reviews on jobs and risk management on partnered schemes.

There is a clear perception to move away from adversarilaism. The partnering has been championed by John Moss with workshops not being restricted to the main team leaders and internal seminars and meetings held for discussion.

Talks to section consultants rather than the clients.

There is a lack of trust from many clients and the perception is that all the advantages are for the contractor. Believes that the clients often want competitive partnering. Furthermore when agreeing pain share gain share, clients often cap the gains at low levels. Amec feel that they are often biting the bullet in that they must always try to accommodate the client. Not always win:win.

Problems also occur when clients don’t take the last step, i.e. commit to the partnering. They have got ideas form the contractor for sometimes nothing in return, other times the contractor will win the tender but not obtain a long term relationship and have had to work considerably harder in order to win it.

Amec have changed to some extent already. They must identify what distinguishes from the rest. They have 3-4 years pro-activitiy.

Partnering reflects the commercial restraints on the clients for example GMP (Guaranteed Max price).

ICE contract from the clients point of view does have guarantee of enhancing value. Driven clients to maximise value. Clients are under commercial restraints.

It is a matter of course for AMEC to propose partnering to clients.

MOD are trying to formulate guide. Public accountability

‘Internally I haven’t seen a report on CIP’.

Partnering won’t affect reviews of projects.

QA systems are in place

To generate information is often difficult on one off projects and measurement tools are often difficult to generate and implement. Procedures for feed back into estimating depts would be useful such as technical notes which act as a vehicle for spreading throughout the company.

Partnering and innovation go well together

R&D is an important aspect. Should be handled in a similar way to partnering using established relationships.

Partnering with external consultants.

Can encourage a win: win relationship Trying to set up a situation to win. Fees when bid is successful. Incentives important. Give an opportunity to maximise and provide rewards for making savings. For scheduling of materials for example if you make a saving you get a cut (careful not to become too cheap). A joint venture agreement could be arranged and a pain share gain share arrangement could be acceptable but might require a capping of the losses (often not capital rich)

Amec have offered such incentives before partnering but it has now broadened and has produced % savings.

Avoid tying exclusively to one consultant. Consultant often come into contact with clients prior to the contractor and there is a strong possibility that the consultant won’t recommend using the contractor if he has not been selected for a job.

Policy Document

- Should explain to client the policy and strategy. (Clear statement so policy).

- Recommend standardisation

- Checklist of do’s and don’ts

- List potential benefits.

- Include reporting tools for identifying performance

- Need to be able to monitor and access the benefits of partnering.

- Clear commitment.

G Dudley

Marketing Manager and Proposals Manager

Amec

3 Years Southern Practices.

Doesn’t work on partnering projects

There is a strategy here at Amec. Frequent brainstorming, seminars and presentations and experience has been gathered from Newport, Port Sea Clean and the pavement team. The partnering is taking time to filter down to the ranks. Biggest problem is to remove the them and us situation.

Partnering is not a totally new system.

Company has to survive on a profit, the us and them attitude is always underlying. Historically things haven’t always been so bad. 20 years ago there was no problem, 15 years ago auditors appeared then QS’s.

Partnering about communication and with private clients it is no real problem however with public clients you need competition. About 80% of work is private and 20% public.

50% turnover will be with partnering projects such as:

Portsea clean £100M

DBFO £100M

Not successful in hard tendering

Fixed price, reducing cost and adding value is required.

Principle of partnering is good but in practice it doesn’t work to well because not everybody is committed. Principles of partnering learnt so far can be extended into parts of the company.

Committed to partnering, open book and no taking sides approach.

Framework agreements have additional benefits. The pavement teams has resulted in Pavements being cheaper and better than others.

CIP is currently on a learning curve with process mapping procedures underway. It is all about having the ability to look at yourself. It is done with external audits and benchmarking.

EG Rewriting for the job, write a specific procedure for that job. Amec have QA procedures and compare world wide projects.

Individuals on projects are often hard-nosed and projects can be a battle of wits (number tasking for a year).

Individuals and teams need a channel and incentives:

- Personal gain

- Celebrate success

- Identity

Take people out if they are not partnering.

Policy Document

Probably of most use to people who have never used partnering. Partnering should be split not sections such as benchmarking, procurement etc.

Pre-qualification important. And a prequalification presentation is required. Must confirm what we are doing with the procedures involved, benchmarking, goal setting etc.

There are two methods of marketing required those for enlightened clients. You can’t put in a standard pack to cover everybody. Is specific to partners and projects.

Mr J.Dacre

Amec

14 years in company

Estimating Manager

Never worked in partnering scheme and has focused on more traditional forms of contract. Has been involved with the reviewing of target costs on Portsea clean and Newport which are partnering projects however.

Only knows about partnering through monthly management meetings.

Believes clients are not really partnering when they demand a guaranteed max price (GMP).

Strategies are client driven and there therefore no identifiable Amec strategy in place.

The partnering term is up to the client and generally it would seem that partnering is to one sided.

Partnering is used to cut costs and Amec is partnering because it believes it will push down costs.

Partnering should go all the way down the tree

If the will and trust s there partnering will work.

Partnering can be commercially abused.

Selection of personnel is important.

Job should become easier when partnering.

It is not a new phenomena, companies working together and Amec have had similar relationships its suppliers previously. It is difficult to change some people and it is up to the will of individuals largely in making it work.

Partnering can be abused and individuals can be obstructive such as clerk of works and site personnel.

A modification of assessment procedures is required and workshops are important.

Allocation of risks is an important aspect and risks will be transferred when entering a partnering relationship. Risk workshops can be useful along with public accountability. Pain share / gain share needs to be realistic and not over capped.

Partnering affords benefits for the individual regarding

- Improved levels of satisfaction

- Spending time and effort solving technical problems and thereby being self motivating. Partnering changes peoples jobs. People helping each other

The more major the impact on the process the better, such as design up front, buildability etc.

Mustn’t forget the consumption of resources and overheads involved in making a partnering agreement operate effectively.

Thursday 1

Heathrow

Richard Gould

AMEC

Site Agent

18mnths with Amec

Has received backup on partnering in workshops, seminars. Attended the second workshop

Believes that the pavement team are semi partnering. It is not an equal partnership as BAA don’t show their figures and Amec haven’t got control of project costs. There are barriers and BAA are not providing full information.

Amec do not get enough time to finish the project.

QA, process mapping and looking at wasteful steps. Believes that was good enough and the money was in the right place. It was given up with too early

It is reactive rather than proactive.

Standardisation is not present between the three airports.

Feels that the management in Amec and the pavement team are stale ‘BAA clones’, spending all their time doing presentations.

The pavement team should be seen as more successful.

There is not enough continuity.

Morale in manpower is low due to work loss and lack f continuity.

Too much made of continuity

Construction manager was not good and has been removed. He didn’t do anything. (Pampers).

Need more ideas people who are willing to innovate.

There is no real partnering strategy in place.

The fixed fee system is ok.

Amec are making money and have low costs.

Although there is partnering people are still leaving and their is a high turnover of staff. There fore the partnering can’t be a full success.

We don’t expect much from BAA

Direct labour relies on BAA business and continuity. We get the gangs 3-4 months at a time. Direct labour is not the full answer.

There is at present a full filing cabinet of Amec QA procedures. (Amec policy). Best costing, report quicker.

NB. Definitely a them and us feeling at Heathrow.

Improvement areas

Dynamic management committed to improvement

Standardisation of airports procedures and drawings etc for consistency.

Amec people who have been with the company for 25 years are the main problem.

Need our engineers to work with ops and maintenance for a few weeks

A rotational staff policy to avoid people getting stale and keep up interest and motivation.

Clear communication between both sides is required.

Amec to be totally responsible for project costs (don’t see figure at present).

A basket of documents.

Policy Document

Partnering specific procedures are required and it should be easily readable.

Thursday 2

Deckland, Heathrow

Amec

10 years with Amec Rejoined after the partnering started. Framework had been operating for six months. Understood basic principles that were to save 30% costs over 5 years.

Was given no information on partnering and feels that more should have been available especially at the outset.

Generally most people think partnering is a good idea.

Decklan Prefers working with the partnering arrangement. You don’t end up writing letters after letters. It is however a major change in the way that you work especially regarding speed and access. Airfield access and operations. We know more people now so it is better but they should have been more involved in the beginning.

In the pavement team there is a strategy, not sure about AMEC.

Problems generally with BAA

BAA and Amec are partnering but there should be far greater involvement of operation an maintenance.

Senior management need to change more. They are far to tunnel visioned.

People are not willing enough to change and there is not enough team building, especially between operations and the pavement team.

Designers need to talk to all the team not just certain individuals. There is no design at Heathrow, it is at Gatwick. This is not a problem however the computer system is inadequate (e-mails take a day) and this must be improved. BAA won’t allow changes due to security risks. AMEC and BAA computer systems need to be fully integrated.

Updating of standard specifications is required.

No one has discussed new jobs with me.

Policy Document

- Roles should be more clearly specified

- Documents should be explained. Not just told to read it.

- Team building needs to be increased.

- Framework has to work for the future.

Thursday 3

Barry Mercer, Heathrow

Plant  Administrator, AMEC

All three airports

Responsible for ordering the equipment form separate companies.

Not really involved in the partnering.

They do have key suppliers some of which we use at all three airports. There are no agreements at present however so I'’ not working under a partnering arrangement with suppliers. We do not have any selection criteria as the companies we use are all well established and here are not that many of them.

Obtaining passes is a problem sometimes requiring three days notice.

Generally there is an atmosphere of enthusiasm towards partnering.

I always no who to speak to in order to get the job done.

Policy Document

Just what partnering is about.. Should be explained to the team.

Thursday 5

Bill Hartley

Materials Administrator

Heathrow

Been buying for 33 years

1 year in the pavement team

Brief outline of partnering, was a rush and found out as he went along.

Responsibilities

- Mainly construction

- Delivery of materials

- Personnel, Heathrow

Nothing previously known about partnering

Sees everybody as the team

Encouraging the supplier to partner such as Paul Clarke and Greenhams (Tools and clothing). Also tarmac and Redlands. My role is to encourage them to feel part of the team. Greenhams are very enthusiastic

Have a charter in place with them. Affects of the charter signing have been:

- Encouraged them to be responsive to needs

- We have specific people to talk to

- They can wear pavement team badges

- They have work for the duration of the frame work (unless a major thing goes wrong)

- Encourage them to undertake self billing

‘I’m not buying for Amec but for the pavement team’.

We don’t pay very well. £49,000 and hold only £1000. Accounting system won’t pay the whole £50,000 though.

The system running at present for the team has been devised by the team.

It is good if you come up with an idea because you get used to it. Partnering encourages ‘suggestion box’ attitude

Partnering is a great idea. It is time to think things out and improve them. I don’t want to revert back to an adversarial way of working. Work is far more pleasant now. I can plan for the future with the five year plan in place and make some significant savings because of it. Normally you get the tender and start work with no time to plan.

I go for quality. If you no you’ve got the work you will buy better products . for example shovels might be three times the price but you don’t need three time the numbers of shovels. Matters on a long term agreement but not on a short term arrangement.

Improvements

- Not much to improve.

- There are enough meetings

- More information needs to be given to all members about partnering however.

- No demarcation

- Better communication, we tend to get things through the grape vine regarding other jobs

- The team should really be seen as Stanstead, Heathrow and Gatwick as the pavement team and not individually requiring standardisation of procedures etc.

Thursday 6

Andy Wise

AMEC

CQS, Heathrow

1 year with Pavement team. With Amec since 1989. Runs office with Richard.

Deals mainly with BAA QS’s

Project manager

Doesn’t get that involved with agents

Generally QS’s at the other sites

Joined the pavement team after it had been set-up.

No documentation regarding the partnering but policy specifics spread by word of  mouth.

There was more partnering occurring than I thought and this was quite surprising.

Found the change quite unnerving but found it ‘quite easy to change’ and it didn’t take long to get used to it.

Some QS’s will fit into the framework and others will not.

Works closely with BAA QS who is in the same site office.

Some traditional methods are still useful

There are some 25 framework agreements a lot of which are subcontractors who we deal with, 4-5 of which we deal with all the time.

Better the devil you know

Some subs are not open book.

Relationships are a lot better than the traditional as you deal with the same people all the time.

Major aim is for subcontractors to fill out the similar reports and forms regarding costing and timing. Often we don’t know whether we are making money or losing it at a particular point in time and standardised forms will make this much easier to identify. Important to have information when required otherwise complacency can set in a partnering relationship.

There are not that many subs and suppliers we would want on a permanent agreement.

Problems will not be solved unless people change, agents and project managers.

Amec know how to build and it seems that BAA are poking there nose in a lot of the time, they input less and the checkers are unnecessary. The value of the BAA Engineer is debatable. Project managers will say you need them and the agents will say that you don’t.

There is a large division between pay scales with the BAA engineers sometimes getting 40£ instead of £20 for doing the same job.

People are however aware of their responsibilities and there are few Amec problems and most are associated with people and attitudes.

Many people are too relaxed in partnering schemes

Look after Amec first , then the pavement team then BAA.

The input form BAA regarding ideas, technical ability is less than AMEC.

Feels that there is not a professional enough attitude

BAA use checkers to check AMEC work, they are expensive without much input.

Policy Document

Personally I’ve got a good idea of what its about, however roles need to be identified clearly

More targets have to set..

The internal team needs to be developed more and it is sometimes too easy to chat. There has been problems with the holiday atmosphere however most associated with this have gone (bar 2).

More team building. Socially you get to know what people are like. Not necessarily a good thing.

Summary Heathrow Generally

- Generally the team didn’t seem as cohesive

- Some problems with personal relationships

- Individuals saw themselves being employed by specific companies and not the pavement team.

- Seemed to be annoyed about rewards and uncompetitive salaries. BAA salaries, salt in the wound.

- People seemed more individualistic. Used phrases like I saved £1million.

Friday

Dave Meadows

Senior Service engineer M&E

Deals with electrical sub-contracts and service and pre-construction surveys.

7 projects on three airports.

Attended the workshop however wasn’t that impressed. Felt ‘they were talking at us not to us’. No body read the workshop reports. There was no documentation as an output. Furthermore there was no discussion of specific projects. View of workshops from John Moss. All aimed at 30%. Was not clear what Amec were going to gain form the arrangement.

There was a worry at first that BAA might stitch up Amec.

BAA gain from the agreement but Amec do not. Is not a win:win situation.

Thinks BAA will out carry on after the agreement period.

Partnering has made my job more difficult. I have much more responsibility but no additional help

Amount of work has increased..

I battle with agents. Agents do not understand the complexity of the electrical requirements.

BAA staff are not as committed as they have jobs at the end of it.

BAA are treating the partnering as a FAD.

Nic doesn’t know peoples job. Organogram!

There is no definition of roles and responsibilities.

Nic will put people in that he likes personally EG Simon Dukes. The younger people are in elevated positions because they are cheap. They aren’t as capable due to lack of experience. They make mistakes and are not good man managers. It is disaster management.

Senior management can’t decide command structure for team responsibilities.

BAA staff lacking in performance.

I would like to be paid the same as BAA counterpart.

Amec p[procedures have to be incorporated in the pavement team. This is overly complex. The pavement team should be set up as a totally separate company.

Designers and management should not be at jubilee house. Everyone should be on the site. Management team used to be on site have now gone to Jubilee house. Have lost touched because of this. Team is now fragmented and people at jubilee house feel their superior to site people.

I refused to go to jubilee.

There are no approval systems.

Partnering hasn’t helped with communication with the airport. I know who to talk to at the airport but partnering didn’t help this.

I would still choose partnering as there is less confrontation and hassle.

The teams at all the airports are quite identifiable. At Heathrow their all buddies ?!?

Good personal relationshiops are very important.

There is not enough work to directly employ electrical section so LOSC.

Compensation events from sub contracting company still occur.

Nic doesn’t know what I do.

I want more security of work and more money.

There are only three out of the original team remaining. It was a good team.

Policy Document

To make sure that the partnering is sorted out before you start and show how this should be done.

Friday Fin

2 years on the partnership

Working under Dave meadows. Mostly based at Gatwick. Freelance to Amec.

I haven’t been to any of the workshops. Learning by picking it up as I go along.

Main responsibilities are undertaking pre-construction surveys.

With partnering you get a lot more freedom.

Dealing directly with BAA design team (previously by post).

No messing with work that isn’t needed.

Good face to face contact

Could sit one designer in  at the beginning. (Should improve due to greater information between site and designer.)

I know who to talk to in order to get things done.

Gatwick Ltd are not partnering

Stanstead are a partner but haven’t got a clue. Doing the survey was a nightmare. Stanstead keep trying to get involved saying ‘why aren’t we invited to the meetings.

Principle electrical manager at Stanstead says he hasn’t been involved in the partnering arrangement at all. He should be invited to meetings in order to ready for the partnering framework there.

Some of BAA staff are on contract.

Amec whittled out people who were not into partnering and put them onto other things.

The word of site managers was good. I didn’t like the change (reduction in SM’s.).

The money is not great.

There is rivalry when two jobs get going and there is only one store.

There is a massive increase in pavement work.

Things are now self governing but there is a massive amount more paper work. There is a lot to take in. A file of 30 documents.. This can be a problem for new people. Things must be signed off by the section engineer.

The fee system has changed since the start up of the partnering. Before partnering my job wouldn’t exist. It would have been sub-contracted.

Standardisation is a good thing.

Process charts down to site levels will be beneficial. Give site level staff , ground work operatives a process to work to. Good for LOSC.

It is difficult to get the operatives into a team.

Partnering might get repetitive.

## Summary

Cohesiveness of the team not all it might appear.

Considerable Split between Amec and BAA staff

Don’t restrict the partnering by insisting of cost savings  that affect long term quality such as labour.

Next time greater training of operational staff is required up front (though this is recognised I think!)

Boredom with repetitive work. High turnover of personnel.

Mistrust by clients if partnering suggested by the contractor i.e. not client led.

Policy doc recommended to explain to clients the partnering and also to internal staff. Think of who the PD is aimed at.

Long term agreements: partners need to be honest about the constraints they are under which in turn will affect their aims objectives and incentives.

Innovation, and R&D important to partnering. They can be significantly enhanced through collaboration.

Conflicting views between directors concerning the existence of a strategy

Commitment is seen as a problem. (Champions important and  must be committed)

Different marketing required for non enlightened clients and enlightened clients.

Getting people to do the jobs that they are most suited to and that they are motivated to do.

There is a limit to how much you can save. Can’t carry on saving thirty %. What happens then. (some way of assessing how much you can realistically save might be useful PhD)

LT agreements are great for buying. Don’t get cheap rubbish that will only last the duration of the project regarding equipment. Savings through repeat order regarding materials is a major bonus to the project.

A feeling that BAA staff are not as committed as they have a job at the end of the term.

Inequality of pay of BAA counterparts is a serious motivational problem.

Very high turn over of staff regarding the pavement team.

If other frameworks were set-up how about moving onto different jobs at the airports.